## Turner Central Feeds
Item # | Operational Area | Test Scenario | Expected Results | Test Result (Pass or Fail) | Date Tested | Tester | Defects/Comments
1.01 | Archive, Restore and Partial Restore Work-flow | Verify Dalet forwards the archive command to StorNext HSM for media | Dalet forwards the archive command to StorNext HSM for media |  |  | Mai
1.02 | Archive, Restore and Partial Restore Work-flow | Validate StorNext archives the wrapped media in the data tape robot | StorNext archives the wrapped media in the data tape robot |  |  | Mai
1.03 | Archive, Restore and Partial Restore Work-flow | Validate Dalet Application Server discovers the proxies, references them in it's database and change the Status | Dalet Application Server discovers the proxies, references them in it's database and change the Status |  |  | Mai
1.04 | Archive, Restore and Partial Restore Work-flow | Validate Once archived Dalet will delete the wrapped media on the ActiveRaid SAN and change to Dalet status to 'online & Archived' | Once archived Dalet will delete the wrapped media on the ActiveRaid SAN and change to Dalet status to 'online & Archived' |  |  | Mai
1.05 | Archive, Restore and Partial Restore Work-flow | Validate High Resolution media of a Dalet title residing on the data tape robot will never be removed unless it is completely purged from the Dalet system | High Resolution media of a Dalet title residing on the data tape robot will never be removed unless it is completely purged from the Dalet system |  |  | Mai
2.01 | Browsing and Searching Work-flow | Validate From the web interface user can Browse categories and content | From the web interface user can Browse categories and content |  |  | Ron
2.02 | Browsing and Searching Work-flow | Validate From the web interface user can Search for content using search profiles | From the web interface user can Search for content using search profiles |  |  | Ron
2.03 | Browsing and Searching Work-flow | Validate From the web interface user can View and edit metadata of titles (subject to user rights) using the Asset Manager tool | From the web interface user can View and edit metadata of titles (subject to user rights) using the Asset Manager tool |  |  | Ron
2.04 | Browsing and Searching Work-flow | Validate From the web interface user can Add Annotations to the video clips (subject to user rights) using the web version of MediaLogger, which is frame accurate. | From the web interface user can Add Annotations to the video clips (subject to user rights) using the web version of MediaLogger, which is frame accurate. |  |  | Ron
2.05 | Browsing and Searching Work-flow | Validate From the web interface user can Request Exports to EVS or ActiveRaid on-line SAN via drag-and-drop to a specific requests’ category | From the web interface user can Request Exports to EVS or ActiveRaid on-line SAN via drag-and-drop to a specific requests’ category |  |  | Ron
2.06 | Browsing and Searching Work-flow | Validate From the web interface user can Perform Storyboard-like video editing via the Clip Bin or Storyboarder for compilation of shots preparation of EDLs to trim shots / conform EDL | From the web interface user can Perform Storyboard-like video editing via the Clip Bin or Storyboarder for compilation of shots preparation of EDLs to trim shots / conform EDL |  |  | Ron
2.07 | Browsing and Searching Work-flow | Validate From the web interface user can Change the editorial status of a title | From the web interface user can Change the editorial status of a title |  |  | Ron
3.01 | Ingest Work-flow | Validate that feeds requests in Turner's Feed 24/7 tool pass into Dalet Ingest Time Line | Feeds requested in Turner Feeds 24/7 are sent into Dalet Ingest Time Line automatically |  |  | Jamie
3.02 | Ingest Work-flow | Validate Feeds 24/7 requests are locked out of Dalet within 1 hour of feed start | Any changes made in feeds 24/7 within 1 hour of feed start are not passed into Dalet. |  |  | Jamie
3.03 | Ingest Work-flow | Feeds 24/7 requests are auto-assigned to open record channels in Dalet ingest time line | Feeds 24/7 requests are auto-assigned to open record channels in Dalet ingest time line If no channel is open, Dalet notifies operator. |  |  | Jamie
3.04 | Ingest Work-flow | Validate Feeds 24/7 requests that have no open record channel in Dalet Time Line, notification sent to Feeds Coordinator to fix conflict. |  |  |  | Jamie
3.05 | Ingest Work-flow | Validate that Ingest Operators are able to schedule a 'Single' recording using the Dalet Ingest Time Line | Ingest Operators are able to schedule a 'Single' recording using the Dalet ingest Time Line |  |  | Jamie
3.06 | Ingest Work-flow | Validate that Ingest Operators are able to schedule a 'Recurring' recording using the Dalet Ingest Time Line | Ingest Operators are able to schedule a 'Recurring' recording using the Dalet ingest Time Line |  |  | Jamie
3.07 | Ingest Work-flow | Validate that Ingest Operators are able to 'Start an Instant' recording aka 'crash' recording that has not been scheduled in advance | Ingest Operators are able to start an instant recording aka 'crash' recording that has not been scheduled in advance |  |  | Jamie
3.08 | Ingest Work-flow | Verify Feeds 24/7 event requests feed into Dalet X hours before event start | Feeds 24/7 event requests feed into Dalet X hours before event start |  |  | Jamie
3.09 | Ingest Work-flow | Verify Feeds 24/7 event requests come into Dalet with event start/end and pre-determined record pad start/end | Feeds 24/7 event requests come into Dalet with event start/end and pre-determined record pad start/end |  |  | Jamie
3.1 | Ingest Work-flow | Validate Feeds 24/7 events deleted in Feeds 24/7 tool are removed from Dalet Ingest Time Line and free pre-scheduled record channels | Feeds 24/7 events deleted in Feeds 24/7 tool are removed from Dalet Ingest Time Line and free pre-scheduled record channels |  |  | Jamie
3.11 | Ingest Work-flow | Validate Feeds 24/7 event modifications flow into Dalet and update already staged feed record events until 1 hour prior to event start. | Feeds 24/7 event modifications flow into Dalet and update already staged feed record events until 1 hour prior to event start. |  |  | Jamie
3.12 | Ingest Work-flow | Validate Feeds coordinator should not be allowed to book feeds over existing pre-scheduled record channels | Feeds coordinator should not be allowed to book feeds over existing pre-scheduled record channels |  |  | Jamie
3.13 | Ingest Work-flow | Validate that in all methods of recording editing of the material being recorded will be possible within seconds after the recording has started | Editing of the material being recorded will be possible within seconds after the recording has started in Final Cut Pro |  |  | Jamie
3.14 | Ingest Work-flow | Validate that in all methods of recording editing of the material being recorded will be possible within seconds after the recording has started | Editing of the material being recorded will be possible within seconds after the recording has started in Dalet heavy client |  |  | Jamie
3.15 | Ingest Work-flow | Validate that in all methods of recording editing of the material being recorded will be possible within seconds after the recording has started | Editing of the material being recorded will be possible within seconds after the recording has started in Dalet web client |  |  | Jamie
3.16 | Ingest Work-flow | Validate EVS XT Access creates live proxies within seconds of feed record start. | Validate that Proxy matches TC with live feed and quality is matching requirements |  |  | Jamie
3.17 | Ingest Work-flow | Validate Dalet creates MAM proxy within seconds of feed record start. | Validate that Proxy matches TC with live feed and quality is matching requirements |  |  | Jamie
3.18 | Ingest Work-flow | Validate that Dalet forwards record orders to EVS IP Director using EVS XML. EVS XS servers receive commands from IP Director to start and stop recordings. | Dalet forwards record orders to EVS IP Director using EVS XML. EVS XS servers receive commands from IP Director to start and stop recordings. |  |  | Jamie
3.19 | Ingest Work-flow | Validate EVS IP Director receives Dalet file name and record destination | EVS XS records feeds using the destination and filename provided to EVS IP Director by Dalet |  |  | Jamie
3.2 | Ingest Work-flow | Validate EVS XT Access cluster transfers EVS XS recordings to tsportsa and tsportsb san within seconds of recording | EVS XT Access cluster transfers EVS XS recordings to tsportsa and tsportsb san within seconds of recording |  |  | Jamie
3.21 | Ingest Work-flow | Validate feeds transferred to tsports a and b san are identical | Validate feeds transferred to tsports a and b san are identical in filesize, content, length, naming, destination |  |  | Jamie
3.22 | Ingest Work-flow | Validate EVS Proxy is placed in correct destination and with correct meta data on Proxy NAS | EVS Proxy is placed in correct destination and with correct metadata on Proxy NAS |  |  | Jamie
3.23 | Ingest Work-flow | Validate after in-record feed is stopped before scheduled time, all files close properly and are stored on tsports a and b. | Files that are stopped before pre-scheduled time are valid, complete, and fully usable in Dalet and FCP stations. |  |  | Jamie
3.24 | Ingest Work-flow | Validate that the Ingest Operator has the ability to view and monitor all current recordings within the system via the Ingest Time line module | The Ingest Operator has the ability to view and monitor all current recordings within the system via the Ingest Time line module |  |  | Jamie
3.25 | Ingest Work-flow | Validate that the Ingest Operator has the ability to view and monitor all current recordings within the system via the EVS IP Director | Validate that the Ingest Operator has the ability to view and monitor all current recordings within the system via the EVS IP Director |  |  | Jamie
3.26 | Ingest Work-flow | Validate that the Ingest Operator has the ability to load and monitor all current recordings within the system via FCP | Validate that the Ingest Operator has the ability to load and monitor all current recordings within the system via FCP |  |  | Jamie
3.27 | Ingest Work-flow | Validate Feeds 24/7 events provide router channel information to Dalet. | Feeds 24/7 events provide router channel information to Dalet. |  |  | Jamie
3.28 | Ingest Work-flow | Verify feeds 24/7 passes event descriptive data into Dalet. Title, Sport, Teams, date, venue. | feeds 24/7 passes event descriptive data into Dalet. Title, Sport, Teams, date, venue. |  |  | Jamie
3.29 | Ingest Work-flow | Validate Dalet names feed properly based on Feeds 24/7 data and stores to proper location on tsports san | Dalet names feed properly based on Feeds 24/7 data and stores to proper location on tsports san |  |  | Jamie
3.3 | Ingest Work-flow | Validate that on the scheduled Date - Time the Dalet Ingest time line will instruct Turner Sports router to change cross points based on information passed by Turner Feeds 24/7 | Validate that on the scheduled Date - Time the Dalet Ingest time line will instruct Turner Sports router to change cross points based on information passed by Turner Feeds 24/7 |  |  | Jamie
3.31 | Ingest Work-flow | Validate Dalet locks router after channel change for length of event. | Dalet locks router after channel change for length of event. |  |  | Jamie
3.32 | Ingest Work-flow | validate that Feeds coordinator can manually change router cross point in Dalet Ingest time line which then instructs Turner Sports router to change cross points | validate that Feeds coordinator can manually change router cross point in Dalet Ingest time line which then instructs Turner Sports router to change cross points |  |  | Jamie
3.33 | Ingest Work-flow | Validate Feeds 24/7 is offline. Dalet Time Line Ingest changes are made to events. When Feeds 24/7 comes back online events are not overwritten. | Feeds 24/7 is offline. Dalet Time Line Ingest changes are made to events. When Feeds 24/7 comes back online events are not overwritten. |  |  | Jamie
3.34 | Ingest Work-flow | Validate Dalet Time Line Ingest events can be manually locked out from Feeds 24/7 modification by Feed Coord. | Dalet Time Line Ingest events can be manually locked out from Feeds 24/7 modification by Feed Coord. |  |  | Jamie
3.35 | Ingest Work-flow | Validate EVS records on XS channels can be manually started via IP Director if Dalet is offline | EVS records on XS channels can be manually started via IP Director if Dalet is offline |  |  | Jamie
3.36 | Ingest Work-flow | Validate XTAcess transfers start while Dalet is offline to tsports san. | XTAcess transfers start while Dalet is offline to tsports san. |  |  | Jamie
3.37 | Ingest Work-flow | Validate XS feed fails before completion. Second record is started. Need to associate log data to combined feeds after consolidation | XS feed fails before completion. Second record is started. Need to associate log data to combined feeds after consolidation |  |  | Jamie
3.38 | Ingest Work-flow | Verify Only the Windows / MAC tree directory may be imported in Dalet with XML representing the directory structure in the Isilon | Only the Windows / MAC tree directory may be imported in Dalet with XML representing the directory structure in the Isilon |  |  | Jamie
3.39 | Ingest Work-flow | Validate Dalet will migrate existing asset media and meta data held in IPV Curator | Validate migrated media is online and accessible in Dalet. Validate that metadata is online and accessible in Dalet. |  |  | Jamie
3.4 | Ingest Work-flow | Validate Turner Sports will perform the XSL transformations for all MIRA Logs and MIRA Thesaurus that may be imported in Dalet | The MIRA files are deposited into a Dalet metadata import monitored directory then Dalet will automatically import those files. |  |  | Jamie
3.41 | Ingest Work-flow | Validate Dalet will migrate CNN Mira - Archive catalog metadata only | Validate that CNN MIRA archive catalougues migrated by Dalet show as offline video assets |  |  | Jamie
3.42 | Ingest Work-flow | Validate EVS IP Director will retrieve NBA / IDS system or licensee metadata using Dalet API. | EVS IP Director will retrieve NBA / IDS system or licensee metadata using Dalet API. |  |  | Jamie
3.43 | Ingest Work-flow | Validate EVS IP Director will apply NBA / IDS system or licensee metadata to EVS XT clips | EVS IP Director will apply NBA / IDS system or licensee metadata to EVS XT clips |  |  | Jamie
3.44 | Ingest Work-flow | Validate EVS IP Director will retrieve log data from Dalet via Dalet API | Evs operator finds logged clips using Dalet web client and exports selected clips to EVS IP Director. EVS IP Director will retrieve logged clip data from Dalet via Dalet API and display in EVS. |  |  | Jamie
4.01 | Logging | Validate Turner Sports Stainless Sports Logger system will pass live logging data into Dalet via Dalet API | Validate the Stainelss logger is passing live logging data into Dalet |  |  | Mai/Ron
4.02 | Logging | Validate Turner Sports Stainless Sports Logger data is displayed in Dalet Xtend hilite selector within seconds of logged event | Validate that Stainless log data is shown in Dalet Xtend Hilite selector within seconds of live logged event and that events appear continuously |  |  | Mai/Ron
4.03 | Logging | Validate Turner Sports Stainless Sports Logger data is displayed in Dalet heavy client within seconds of logged event | Turner Sports Stainless Sports Logger data is displayed in Dalet heavy client within seconds of logged event |  |  | Mai/Ron
4.04 | Logging | Validate Turner Sports Stainless Sports Logger data is displayed in Dalet web client within seconds of logged event | Turner Sports Stainless Sports Logger data is displayed in Dalet web client within seconds of logged event |  |  | Mai/Ron
4.05 | Logging | Validate NBA / IDS system or licensee metadata will be imported in the Sports Stainless Live Logger application | Validate that NBA / IDS system or licensee metadata, rosters, scores, timing will be imported in the Sports Stainless Live Logger application |  |  | Mai/Ron
4.06 | Logging | Validate Sports Stainless Live Logger passes NBA / IDS system or licensee metadata into Dalet Database | Validate Sports Stainless Live Logger passes NBA / IDS system or licensee metadata metadata, rosters, scores, timing into Dalet Database. Data goes with log as well. |  |  | Mai/Ron
4.07 | Logging | Validate Live Logging will be performed on Stainless Sports logger against EVS proxy | Validate that logger can log events while feed is in record using Evs proxy |  |  | Mai/Ron
4.08 | Logging | Validate Logger can select and open in-record feeds | Validate that Stainless logger can view all in-record feeds from Dalet API. Validate that operator can select feed and load into logger. Verify that correct proxy for selected event loads. |  |  | Mai/Ron
4.09 | Logging | Validate Logger can see external roster data for selected event | Logger can see external roster data for selected event |  |  | Mai/Ron
4.1 | Logging | Validate Logger can see external scoring data for selected events | Logger can see external scoring data for selected events |  |  | Mai/Ron
4.11 | Logging | Validate Logger can see external timing data for selected events | Logger can see external timing data for selected events |  |  | Mai/Ron
4.12 | Logging | Validate In case external data feeds are unavailable roster data can be entered manually in Sport logger | In case external data feeds are unavailable roster data can be entered manually in Sport logger |  |  | Mai/Ron
4.13 | Logging | Validate Verify logged event time code matches feed and proxy time code | Verify logged event time code matches feed and proxy time code |  |  | Mai/Ron
4.14 | Logging | Validate Verify multiple loggers can be opened on one machine at the same time. | Verify multiple loggers can be opened on one machine at the same time. |  |  | Mai/Ron
4.15 | Logging | Validate Verify that in a multiple logger open use case, all different feed logs operate correctly. | Verify that in a multiple logger open use case, all different feed logs operate correctly. |  |  | Mai/Ron
4.16 | Logging | Validate In Dalet operator can find and send events to logger | In Dalet operator can find and send events to logger |  |  | Mai/Ron
4.17 | Logging | Validate Run on MAC OS X (10.6) or Parallels Desktop (version 5 or 6) on a Desktop iMAC. | Run on MAC OS X (10.6) or Parallels Desktop (version 5 or 6) on a Desktop iMAC. |  |  | Mai/Ron
4.18 | Logging | Validate Support for multiple sports (team and individual sports). | Support for multiple sports (team and individual sports). |  |  | Mai/Ron
4.19 | Logging | Validate Log via Proxies from growing, , offline, and closed files. | Log via Proxies from growing, , offline, and closed files. |  |  | Mai/Ron
4.2 | Logging | Validate Ability to save logger/sport templates for quick event setup. | Ability to save logger/sport templates for quick event setup. |  |  | Mai/Ron
4.21 | Logging | Validate Logger should support customizable user interface with single-click setup via Roster lists and Action buttons. (See Customizable user interface below). | Logger should support customizable user interface with single-click setup via Roster lists and Action buttons. (See Customizable user interface below). |  |  | Mai/Ron
4.22 | Logging | Validate Customized Event Information Pane (See Event Information Pane Subsection) | Customized Event Information Pane (See Event Information Pane Subsection) |  |  | Mai/Ron
4.23 | Logging | Validate Customizable Keyboard shortcuts that can be setup and saved with the templates (See Keyboard Shortcuts subsection below). | Customizable Keyboard shortcuts that can be setup and saved with the templates (See Keyboard Shortcuts subsection below). |  |  | Mai/Ron
4.24 | Logging | Validate Milestone and Start/Stop support with handles that can be defined per sport/league. | Milestone and Start/Stop support with handles that can be defined per sport/league. |  |  | Mai/Ron
4.25 | Logging | Validate Search, Filter, and Sort functionality in logger. Must be able to search each field as well as a global search. Must be able to Sort all fields in the logger data sheet. | Search, Filter, and Sort functionality in logger. Must be able to search each field as well as a global search. Must be able to Sort all fields in the logger data sheet. |  |  | Mai/Ron
4.26 | Logging | Validate Customizable Rating System that can display the data in different colors which is then passed to the Final Cut Pro Hilite Selector and Dalet MAM. | Customizable Rating System that can display the data in different colors which is then passed to the Final Cut Pro Hilite Selector and Dalet MAM. |  |  | Mai/Ron
4.27 | Logging | Validate Operator can flag a log event. Flag must display in Dalet MAM. | Operator can flag a log event. Flag must display in Dalet MAM. |  |  | Mai/Ron
4.28 | Logging | Validate Export entire log for a game as a simple flattened file report, XML, Excel, text. | Export entire log for a game as a simple flattened file report, XML, Excel, text. |  |  | Mai/Ron
4.29 | Logging | Validate Print entire log sheet and/or print selected log events to external printer or PDF. Birth certificate remains header of printout. | Print entire log sheet and/or print selected log events to external printer or PDF. Birth certificate remains header of printout. |  |  | Mai/Ron
4.3 | Logging | Validate Submit start, end and actual log point of all events to Dalet MAM | Submit start, end and actual log point of all events to Dalet MAM |  |  | Mai/Ron
4.31 | Logging | Validate All field configurations can be done by Turner on site without requesting changes from vendor. | All field configurations can be done by Turner on site without requesting changes from vendor. |  |  | Mai/Ron
4.32 | Logging | Validate Logger must support action buttons for quick and easy entry. | Logger must support action buttons for quick and easy entry. |  |  | Mai/Ron
4.33 | Logging | Validate Action buttons should be able to be configured via Sport/League. | Action buttons should be able to be configured via Sport/League. |  |  | Mai/Ron
4.34 | Logging | Validate Support for Actions buttons which are global | Support for Actions buttons which are global |  |  | Mai/Ron
4.35 | Logging | Validate Support for the creation of categories and sub-categories for global and sport/league Action buttons. | Support for the creation of categories and sub-categories for global and sport/league Action buttons. |  |  | Mai/Ron
4.36 | Logging | Validate Allow for multiple selections in a single Sub-category. | Allow for multiple selections in a single Sub-category. |  |  | Mai/Ron
4.37 | Logging | Validate Action buttons should be linked to player which allows for relationship. | Action buttons should be linked to player which allows for relationship. |  |  | Mai/Ron
4.38 | Logging | Validate Free text fields available for entry | Free text fields available for entry. |  |  | Mai/Ron
4.39 | Logging | Validate Fields can have drop down selections. | Fields can have drop down selections. |  |  | Mai/Ron
4.4 | Logging | Validate Log from file based streams which may include FLV, MOV(h.264), and MP4 in addition to EVS TS proxy format. | Log from file based streams which may include FLV, MOV(h.264), and MP4 in addition to EVS TS proxy format. |  |  | Mai/Ron
4.41 | Logging | Validate Viewer capabilities (DVR) | Viewer capabilities (DVR) |  |  | Mai/Ron
4.42 | Logging | Validate Dynamic Fast Forward single button control (2x ,4x and 8x), Seek backward interval control (10 seconds, 30 seconds, 1 minute, 2 minutes, 5 minutes) | Dynamic Fast Forward single button control (2x ,4x and 8x), Seek backward interval control (10 seconds, 30 seconds, 1 minute, 2 minutes, 5 minutes) |  |  | Mai/Ron
4.43 | Logging | Validate Single frame jog forward and reverse | Single frame jog forward and reverse |  |  | Mai/Ron
4.44 | Logging | Validate Type and seek specific Time code | Type and seek specific Time code |  |  | Mai/Ron
4.45 | Logging | Verify Time line Shuttle control to drag forward and reverse randomly | Time line Shuttle control to drag forward and reverse randomly |  |  | Mai/Ron
4.46 | Logging | Validate Log events highlighted in time line and via log data pop-ups | Log events highlighted in time line and via log data pop-ups |  |  | Mai/Ron
4.47 | Logging | Validate Seek to Beginning and End of proxy (Seek to LIVE). | Seek to Beginning and End of proxy (Seek to LIVE). |  |  | Mai/Ron
4.48 | Logging | Validate Go to In/Go to Out on event of selected log. | Go to In/Go to Out on event of selected log. |  |  | Mai/Ron
4.49 | Logging | Validate Loading a log, loads matching proxy automatically | Loading a log, loads matching proxy automatically |  |  | Mai/Ron
4.5 | Logging | Validate Event information pane must be able to be customized per sport/league with customizable fields for each. | Event information pane must be able to be customized per sport/league with customizable fields for each. |  |  | Mai/Ron
4.51 | Logging | Validate Fields must be able to be modified at Turner. | Fields must be able to be modified at Turner. |  |  | Mai/Ron
4.52 | Logging | Validate Fields should be allowed to be set as a required field. | Fields should be allowed to be set as a required field. |  |  | Mai/Ron
4.53 | Logging | Validate Event information pane should allow for configurable drop-downs. | Event information pane should allow for configurable drop-downs. |  |  | Mai/Ron
4.54 | Logging | Validate Event information data must pass to Dalet MAM and be associated with the Master Clip. | Event information data must pass to Dalet MAM and be associated with the Master Clip. |  |  | Mai/Ron
4.55 | Logging | Validate Birth certificate from Dalet pre-populates log data. | Birth certificate from Dalet pre-populates log data. |  |  | Mai/Ron
4.56 | Logging | Validate Action Categories and Sub-Categories need to be able to be assigned keyboard shortcuts. | Action Categories and Sub-Categories need to be able to be assigned keyboard shortcuts. |  |  | Mai/Ron
4.57 | Logging | Validate Viewer controls should be able to be controlled via Keyboard shortcuts: J, K, L for Rewind, Play, Fast forward. | Viewer controls should be able to be controlled via Keyboard shortcuts: J, K, L for Rewind, Play, Fast forward. |  |  | Mai/Ron
4.58 | Logging | Validate In and Out Points should be allowed for keyboard shortcuts: I for Start, O for Stop and ENTER for Milestone. | In and Out Points should be allowed for keyboard shortcuts: I for Start, O for Stop and ENTER for Milestone. |  |  | Mai/Ron
4.59 | Logging | Validate Keyboard shortcuts are configurable by Turner based on template, not on user. | Keyboard shortcuts are configurable by Turner based on template, not on user. |  |  | Mai/Ron
4.6 | Logging | Validate List of clips should be individually selected or automatically selected based on user selected metadata i.e. “all dunks”. | List of clips should be individually selected or automatically selected based on user selected metadata i.e. “all dunks”. |  |  | Mai/Ron
4.61 | Logging | Validate When previously logged events are changed in Sports logger, event is updated in Dalet MAM. | When previously logged events are changed in Sports logger, event is updated in Dalet MAM. |  |  | Mai/Ron
4.62 | Logging | Validate Loggers and Final Cut Integrations should automatically fail-over to new dbase in the case of a primary failure. | Loggers and Final Cut Integrations should automatically fail-over to new dbase in the case of a primary failure. |  |  | Mai/Ron
4.63 | Logging | Validate Database must allow direct query or offer matching web services for query. | Database must allow direct query or offer matching web services for query. |  |  | Mai/Ron
4.64 | Logging | Validate Number of log seats must be expandable and able to be installed without shutting down the entire log system or database. | Number of log seats must be expandable and able to be installed without shutting down the entire log system or database. |  |  | Mai/Ron
4.65 | Logging | Validate Ability to select logged plays from the log sheet to create a shot sheet. | Ability to select logged plays from the log sheet to create a shot sheet. |  |  | Mai/Ron
4.66 | Logging | Validate Shot Sheet should be able to be saved in a Word or Excel document, edited, and printed (view, print, and edit from logger) | Shot Sheet should be able to be saved in a Word or Excel document, edited, and printed (view, print, and edit from logger) |  |  | Mai/Ron
4.67 | Logging | Validate Changes in logging template XML populates to logger UI. | Changes in logging template XML populates to logger UI. |  |  | Mai/Ron
5.01 | Login / Authentication | Verify that Login - Field validations is performed successfully | Login - Field validations is performed successfully |  |  | Ron/Mai/Jamie
5.02 | Login / Authentication | Verify that Login Fails and the appropriate error message is displayed when the user enters an invalid username and Password | Login Fails and the appropriate error message is displayed |  |  | Ron/Mai/Jamie
5.03 | Login / Authentication | Validate that Login is successful when the user enters a valid username and Password | Login is successful |  |  | Ron/Mai/Jamie
5.04 | Login / Authentication | Validate that the user can Logout successfully | The user logs out successfully |  |  | Ron/Mai/Jamie
5.05 | Login / Authentication |  |  |  |  | Ron/Mai/Jamie
5.06 | Login / Authentication | Verify that Login - Field validations is performed successfully | Login - Field validations is performed successfully |  |  | Ron/Mai/Jamie
5.07 | Login / Authentication | Verify that Login Fails and the appropriate error message is displayed when the user enters an invalid username and Password | Login Fails and the appropriate error message is displayed |  |  | Ron/Mai/Jamie
5.08 | Login / Authentication | Validate that Login is successful when the user enters a valid username and Password | Login is successful |  |  | Ron/Mai/Jamie
5.09 | Login / Authentication | Validate that the user can Logout successfully | The user logs out successfully |  |  | Ron/Mai/Jamie
5.1 | Login / Authentication |  |  |  |  | Ron/Mai/Jamie
5.11 | Login / Authentication | Verify that Login - Field validations is performed successfully | Login - Field validations is performed successfully |  |  | Ron/Mai/Jamie
5.12 | Login / Authentication | Verify that Login Fails and the appropriate error message is displayed when the user enters an invalid username and Password | Login Fails and the appropriate error message is displayed |  |  | Ron/Mai/Jamie
5.13 | Login / Authentication | Validate that Login is successful when the user enters a valid username and Password | Login is successful |  |  | Ron/Mai/Jamie
5.14 | Login / Authentication | Validate that the user can Logout successfully | The user logs out successfully |  |  | Ron/Mai/Jamie
5.15 | Login / Authentication |  |  |  |  | Ron/Mai/Jamie
5.16 | Login / Authentication | Verify that Login - Field validations is performed successfully | Login - Field validations is performed successfully |  |  | Ron/Mai/Jamie
5.17 | Login / Authentication | Verify that Login Fails and the appropriate error message is displayed when the user enters an invalid username and Password | Login Fails and the appropriate error message is displayed |  |  | Ron/Mai/Jamie
5.18 | Login / Authentication | Validate that Login is successful when the user enters a valid username and Password | Login is successful |  |  | Ron/Mai/Jamie
5.19 | Login / Authentication | Validate that the user can Logout successfully | The user logs out successfully |  |  | Ron/Mai/Jamie
5.2 | Login / Authentication |  |  |  |  | Ron/Mai/Jamie
5.21 | Login / Authentication | Verify that Login - Field validations is performed successfully | Login - Field validations is performed successfully |  |  | Ron/Mai/Jamie
5.22 | Login / Authentication | Verify that Login Fails and the appropriate error message is displayed when the user enters an invalid username and Password | Login Fails and the appropriate error message is displayed |  |  | Ron/Mai/Jamie
5.23 | Login / Authentication | Validate that Login is successful when the user enters a valid username and Password | Login is successful |  |  | Ron/Mai/Jamie
5.24 | Login / Authentication | Validate that the user can Logout successfully | The user logs out successfully |  |  | Ron/Mai/Jamie
5.25 | Login / Authentication | Verify that Login - Field validations is performed successfully | Login - Field validations is performed successfully |  |  | Ron/Mai/Jamie
5.26 | Login / Authentication | Verify that Login Fails and the appropriate error message is displayed when the user enters an invalid username and Password | Login Fails and the appropriate error message is displayed |  |  | Ron/Mai/Jamie
5.27 | Login / Authentication | Validate that Login is successful when the user enters a valid username and Password | Login is successful |  |  | Ron/Mai/Jamie
5.28 | Login / Authentication | Validate that the user can Logout successfully | The user logs out successfully |  |  | Ron/Mai/Jamie
5.29 | Login / Authentication | Validate User only sees content authorized | User only sees content authorized |  |  | Ron/Mai/Jamie
5.3 | Login / Authentication | Validate Dalet Xtend plugin should carry FCP highlight user login and permissions automatically | Dalet Xtend plugin should carry FCP highlight user login and permissions automatically |  |  | Ron/Mai/Jamie
5.31 | Login / Authentication | Validate All systems authenticate using Turner Active Directory logins | All systems authenticate using Turner Active Directory logins |  |  | Ron/Mai/Jamie
5.32 | Login / Authentication | Validate Dalet Service Accounts have needed access to Turner storage systems | Dalet Service Accounts have needed access to Turner storage systems |  |  | Ron/Mai/Jamie
6.01 | Media Asset Management Work-flow | Validate Turner will define categories fro catalougues in the Cataloging Work-flow | Turner will define categories fro catalougues in the Cataloging Work-flow. |  |  | Jamie
6.02 | Media Asset Management Work-flow | Validate User enters metadata related to an entire media asset using Dalet Asset Management Form | User enters metadata related to an entire media asset using Dalet Asset Management Form |  |  | Jamie
6.03 | Media Asset Management Work-flow | Validate ADMIN defines various metadata Forms by different 'Types of Assets' and different 'Types of users' | ADMIN defines various metadata Forms by different 'Types of Assets' and different 'Types of users' |  |  | Jamie
6.04 | Media Asset Management Work-flow | Validate Proper Form is presented to the user based on rights and asset type | Proper Form is presented to the user based on rights and asset type |  |  | Jamie
6.05 | Media Asset Management Work-flow | Validate Can add Locators ( time-coded annotations) to Video using Dalet MediaLogger. Locators are carried into FCP. | Can add Locators ( time-coded annotations) to Video using Dalet MediaLogger. Locators are carried into FCP. |  |  | Jamie
6.06 | Media Asset Management Work-flow | Validate The set of Locators available to a user depend on the Group the user belongs to. | The set of Locators available to a user depend on the Group the user belongs to. |  |  | Jamie
6.07 | Media Asset Management Work-flow | Validate Frame-accurate logging performed using the proxy formats in DaletPlus Windows | Frame-accurate logging performed using the proxy formats in DaletPlus Windows |  |  | Jamie
6.08 | Media Asset Management Work-flow | Validate Frame-accurate logging performed using the proxy formats in a Web-space web client | Frame-accurate logging performed using the proxy formats in a Web-space web client |  |  | Jamie
6.09 | Media Asset Management Work-flow | Validate User can change the asset status to 'Logged' | User can change the asset status to 'Logged' |  |  | Jamie
6.1 | Media Asset Management Work-flow | Validate User can change the asset status to 'Logged' | Send an email upon completion of an ingest job. |  |  | Jamie
6.11 | Media Asset Management Work-flow | Validate user can Send an email upon completion of a Migration Action | Send an email upon completion of a Migration Action |  |  | Jamie
6.12 | Media Asset Management Work-flow | Validate User interface to modify SoM (Start TC) in Verify Media Properties dialog. | User interface to modify SoM (Start TC) in Verify Media Properties dialog. |  |  | Jamie
6.13 | Media Asset Management Work-flow | Validate Auto pop-up of the Dalet Asset Manager form through Scheduled Recording dialog in Ingest Time line | Auto pop-up of the Dalet Asset Manager form through Scheduled Recording dialog in Ingest Time line |  |  | Jamie
6.14 | Media Asset Management Work-flow | Validate Smart parsing of media files imported by drag and drop into the heavy client. | Smart parsing of media files imported by drag and drop into the heavy client. |  |  | Jamie
6.15 | Media Asset Management Work-flow | Validate user can send EVS IP Director schedule record shortening / extending orders of an already started recording using EVS IP Director XML (if supported by EVS). | · send EVS IP Director schedule record shortening / extending orders of an already started recording using EVS IP Director XML (if supported by EVS). |  |  | Jamie
6.16 | Media Asset Management Work-flow | Validate user can receive EVS IP Director schedule record acknowledgments using EVS IP Director XML. | · receive EVS IP Director schedule record acknowledgments using EVS IP Director XML. |  |  | Jamie
6.17 | Media Asset Management Work-flow | Validate user can receive EVS IP Director growing recording media information using EVS IP Director API. | · receive EVS IP Director growing recording media information using EVS IP Director API. |  |  | Jamie
6.18 | Media Asset Management Work-flow | Validate Media Discovery Integration: discover media created in the EVS Network if EVS sends an XML | Media Discovery Integration: discover media created in the EVS Network if EVS sends an XML |  |  | Jamie
6.19 | Media Asset Management Work-flow | Validate Download media while recording in EVS Network using EVS XT Access XML. | Download media while recording in EVS Network using EVS XT Access XML. |  |  | Jamie
6.2 | Media Asset Management Work-flow | Validate receive EVS LSM clip metadata (selected on EVS IP Director) using EVS XT Access XML | receive EVS LSM clip metadata (selected on EVS IP Director) using EVS XT Access XML |  |  | Jamie
6.21 | Media Asset Management Work-flow | Validate send Dalet Video Clip Title (logical sub-clip to a parent asset) to EVS IP Director using EVS IP Director API or XML. | send Dalet Video Clip Title (logical sub-clip to a parent asset) to EVS IP Director using EVS IP Director API or XML. |  |  | Jamie
6.22 | Media Asset Management Work-flow | Validate A dedicated Dalet Category / Dalet Media Migration Policy configuration will transfer to a dedicated EVS: -frame -bin -page | A dedicated Dalet Category / Dalet Media Migration Policy configuration will transfer to a dedicated EVS: -frame -bin -page |  |  | Jamie
6.23 | Media Asset Management Work-flow | Validate the user can Generate a ‘DaletPlus friendly’ proxy and streaming formats from EVS-generated ProRes media in while scenario | Generate a ‘DaletPlus friendly’ proxy and streaming formats from EVS-generated ProRes media in while scenario |  |  | Jamie
6.24 | Media Asset Management Work-flow | VerifyImport EVS-generated low-res MPEG-2 TS H.264 in while scenario | Import EVS-generated low-res MPEG-2 TS H.264 in while scenario |  |  | Jamie
6.25 | Media Asset Management Work-flow | Verify Import EVS-generated low-res MPEG-2 E.S. long GOP in while scenario | Import EVS-generated low-res MPEG-2 E.S. long GOP in while scenario |  |  | Jamie
6.26 | Media Asset Management Work-flow | Verify “Complex Locators” conceptual data model, which is already under development, to better support Sports Logging Tool complex locators (metadata tracks). | “Complex Locators” conceptual data model, which is already under development, to better support Sports Logging Tool complex locators (metadata tracks). |  |  | Jamie
6.27 | Media Asset Management Work-flow | Verify Export XML to Sports Logging Tool to indicate which asset to log[5] | Export XML to Sports Logging Tool to indicate which asset to log[5] |  |  | Jamie
6.28 | Media Asset Management Work-flow | Verify Partial restore of files in ProRes LT using Quantum SNSM. | Partial restore of files in ProRes LT using Quantum SNSM. |  |  | Jamie
6.29 | Media Asset Management Work-flow | Verify Render cut-only EDLs onto ProRes LT high-res media when editing in DaletPlus; or when clicking ‘Render Selected’ (trimming) or ‘Render All’ (conforming) in WebSpace. | Render cut-only EDLs onto ProRes LT high-res media when editing in DaletPlus; or when clicking ‘Render Selected’ (trimming) or ‘Render All’ (conforming) in WebSpace. |  |  | Jamie
6.3 | Media Asset Management Work-flow | Verify Auto refresh (in order for Sports Logging Tool logs to appears automatically in the Hilites Selector UI) | Auto refresh (in order for Sports Logging Tool logs to appears automatically in the Hilites Selector UI) |  |  | Jamie
6.31 | Media Asset Management Work-flow | Verify Browse by event (rather than Category) | Browse by event (rather than Category) |  |  | Jamie
6.32 | Media Asset Management Work-flow | Verify displayed fields | Displayed Fields[7] |  |  | Jamie
6.33 | Media Asset Management Work-flow | Verify Global Search in ”Hilites Selector” | Global Search in ”Hilites Selector” |  |  | Jamie
6.34 | Media Asset Management Work-flow | Verify Send FCP media and XML EDL with relative paths | Send FCP media and XML EDL with relative paths |  |  | Jamie
6.35 | Media Asset Management Work-flow | Verify Allow the use of “Send to NLE” from DaletPlus or WebSpace even if the media is archived thus not accessible by FCP editors, and trigger partial restore requests to Quantum SNSM. | Allow the use of “Send to NLE” from DaletPlus or WebSpace even if the media is archived thus not accessible by FCP editors, and trigger partial restore requests to Quantum SNSM. |  |  | Jamie
6.36 | Media Asset Management Work-flow | Verify Partial restore of EDL segments into a new EDL | Partial restore of EDL segments into a new EDL |  |  | Jamie
6.37 | Media Asset Management Work-flow | Verify Mapping Dalet Locators color to FCP marker color. | Mapping Dalet Locators color to FCP marker color. |  |  | Jamie
6.38 | Media Asset Management Work-flow | Verify FCP Export through Dalet Xtend will maintain genealogy. | FCP Export through Dalet Xtend will maintain genealogy. |  |  | Jamie
6.39 | Media Asset Management Work-flow | Verify FCP Export through Dalet Xtend will maintain markers | FCP Export through Dalet Xtend will maintain markers |  |  | Jamie
6.4 | Media Asset Management Work-flow | Verify When importing EDL / Video Title / Video Clip into FCP through Xtend, only predefined families of locators will be imported into FCP. | When importing EDL / Video Title / Video Clip into FCP through Xtend, only predefined families of locators will be imported into FCP. |  |  | Jamie
6.41 | Media Asset Management Work-flow | Verify Pull-down metadata fields in the Dalet Xtend Export dialog box | Pull-down metadata fields in the Dalet Xtend Export dialog box |  |  | Jamie
6.42 | Media Asset Management Work-flow | Verify Keyboard shortcut to "Link to category..." or to "Migrate Media by Policy --> ...". | Keyboard shortcut to "Link to category..." or to "Migrate Media by Policy --> ...". |  |  | Jamie
6.43 | Media Asset Management Work-flow | Verify Thumbnails support for graphic assets in the data model only (no automatic generation of those thumbnails) | Thumbnails support for graphic assets in the data model only (no automatic generation of those thumbnails) |  |  | Jamie
6.44 | Media Asset Management Work-flow | Verify ‘Image Sequence’ new asset type. | ‘Image Sequence’ new asset type. |  |  | Jamie
6.45 | Media Asset Management Work-flow | Verify Job Monitor in WebSpace | Job Monitor in WebSpace |  |  | Jamie
6.46 | Media Asset Management Work-flow | Verify Solution for streaming to WebSpace while streaming format is still being generated | Solution for streaming to WebSpace while streaming format is still being generated |  |  | Jamie
6.47 | Media Asset Management Work-flow | Verify Search Engine with spell checking, stemming and synonyms | Search Engine with spell checking, stemming and synonyms |  |  | Jamie
6.48 | Media Asset Management Work-flow | Verify A “smart” search engine that employs authority control and can correct for user error, as well as search on similar or truncated terms. | A “smart” search engine that employs authority control and can correct for user error, as well as search on similar or truncated terms. |  |  | Jamie
6.49 | Media Asset Management Work-flow | Verify Trimmed original feed clips, logs remain attached and FCP can reconnect media with new clip | Trimmed original feed clips, logs remain attached and FCP can reconnect media with new clip |  |  | Jamie
6.5 | Media Asset Management Work-flow | Verify Users can specify Media to be held and not deleted. | Users can specify Media to be held and not deleted. |  |  | Jamie
6.51 | Media Asset Management Work-flow | Verify Full asset purge deletes both hi res and proxy media | Full asset purge deletes both hi res and proxy media |  |  | Jamie
7.01 | Production Formats | Validate that the correct Dalet Ingest, Editing and Rendering formats in ActiveRaid on-line SAN / Dalet production storage are used | The following Dalet Ingest, Editing and Rendering formats in ActiveRaid on-line SAN / Dalet production storage are used: Code:ProRes100 LT HD 1080/59.94 1920x1080; with 16 PCM mono 24bit and 16bit 48KHz audio tracks |  |  | Ron
7.02 | Production Formats | Validate that the correct Turner Sports Historical formats are used | The following Turner Sports Historical formats are used: 1. Codec: XDCamHD422, 50 mbit 2. Codec:DVCPro100 HD 1080i/59.94 1980x1080 with 8 PCM mono 16bit, 48KHz audio tracks |  |  | Ron
7.03 | Production Formats | Validate that the correct Low resolution media formats are used for Dalet WebSpace web clients: | The following low resolution media format is used for Dalet WebSpace web clients: Codec:H264 1Mbps 16:9 640x360 with 8 interleaved stereo (treated as 16 mono) AAC 16bit, 48KHz audio tracks, and 8 non-interleaved store MPEG-1 Layer 2 16bits, 48KHz, 128 kbps audio files |  |  | Ron
7.04 | Production Formats | Validate that the correct Low resolution media formats are used for DaletPlus Windows clients: | The following low resolution media format is used for DaletPlus Windows clients: 1. Codec:H264 1Mbps 16:9 640x480 with 8 interleaved store (treated as 16 mono) AAC 16bit, 48KHz audio tracks, and 8 non-interleaved store MPEG-1 Layer 2 16bits, 48KHz, 128 kbps audio files 2. Codec: MPEG2 I-frame only 5 Mbps 16:9 480x360 with 8 non-interleaved MPEG -I Layer-2 store (treated as 16 mono) 16bit, 48KHz, 128 kbps audio tracks |  |  | Ron
7.05 | Production Formats | Validate that the correct Low resolution media formats are used for Stainless logger clients | The following low resolution media formats are used for DaletPlus Windows clients: 1. Codec: MPEG2 I-frame only 5 Mbps 16:9 480x360 with 8 non-interleaved MPEG -I Layer-2 store (treated as 16 mono) 16bit, 48KHz, 128 kbps audio tracks 2. Codec:H264 1Mbps 16:9 640x480 with 8 interleaved store (treated as 16 mono) AAC 16bit, 48KHz audio tracks, and 8 non-interleaved store MPEG-1 Layer 2 16bits, 48KHz, 128 kbps audio files |  |  | Ron
7.06 | Production Formats | Validate that the correct Dalet Exported formats are used | The following Dalet Exported formats are used: native format of stored media |  |  | Ron
7.07 | Production Formats | Validate Dalet allows for checkin and storage of any media format using the "unknown format" container. |  |  |  | Ron
7.08 | Production Formats | Validate Turner Sports Audio formats are supported by Dalet | WAV and AIFF and MP3 (see samples provided by Turner) |  |  | Ron
7.09 | Production Formats | Validate Dalet will store FCP Projects | Dalet will store FCP Projects |  |  | Ron
8.01 | Production Work-flow | Validate Instant Replay will be performed on EVS XT3 servers from in-record feeds on EVS XS | Validate that Instant Replay can be performed on all XT3 server play-out channels while recording feeds on all XS server channels |  |  | Ron
8.02 | Production Work-flow | Validate XT server clips are passed to IP Director | Validate that Clips created on the XT play-out server are passed to EVS IP Director |  |  | Ron
8.03 | Production Work-flow | Validate EVS Operators can use IP Director to send clips to Dalet MAM | Validate that EVS IP Director managed clips that need to be preserved to MAM are selected by the EVS operator and sent to Dalet MAM via EVS IP Director integration with Dalet API. Validate that clips sent match original IN/OUT points and metadata. |  |  | Ron
8.04 | Production Work-flow | Validate Content in the Dalet MAM residing on tsports SAN will be transferred to the EVS IP Director | Validate that content selected in the Dalet MAM by the EVS operator using Dalet web client that is stored on tsports SAN can be transferred to the EVS IP Director for play-out on XT3 server.Validate that clips sent match original IN/OUT points and metadata. |  |  | Ron
8.05 | Production Work-flow | Validate Content in the Dalet MAM residing in Tape Archive will be transferred to the EVS IP Director | Validate that content selected in the Dalet MAM by the EVS operator using Dalet web client that is stored on Tape Archive can be transferred to the EVS IP Director for play-out on XT3 server. Validate that clips sent match original IN/OUT points and metadata. |  |  | Ron
8.06 | Production Work-flow | Validate FCP selects clip in Dalet Xtend and loads into FCP via drag-drop | Validate that clip lands in FCP bin and are playable with correct metadata |  |  | Ron
8.07 | Production Work-flow | Validate FCP selects clip in Dalet Xtend and loads into FCP via button | Validate that clip lands in FCP bin and are playable with correct metadata |  |  | Ron
8.08 | Production Work-flow | Validate FCP can search for clips in Dalet Xtend | FCP can search for clips in Dalet Xtend |  |  | Ron
8.09 | Production Work-flow | Validate FCP can audition clips in Dalet Xtend | FCP can audition clips in Dalet Xtend |  |  | Ron
8.1 | Production Work-flow | Validate FCP can sort all clip fields in Dalet xtend | FCP can sort all clip fields in Dalet xtend |  |  | Ron
8.11 | Production Work-flow | Validate When exporting via Dalet Xtend in FCP menu, FCP operator is required to enter metadata fields | When exporting via Dalet Xtend in FCP menu, FCP operator is required to enter metadata fields |  |  | Ron
8.12 | Production Work-flow | Validate FCp can export to MAM using Dalet Xtend in FCP menu | Verify that exported clip lands with correct metadata and matching code and is playable. |  |  | Ron
8.13 | Production Work-flow | Validate FCP can export to EVS using Dalet Xtend in FCP menu | Verify that correct target frame and page is where clip lands. Also verify correct folder in IP Director is where it lands. |  |  | Ron
8.14 | Production Work-flow | Validate FCP can export to Archive using Dalet Xtend in Fcp menu | FCP can export to Archive using Dalet Xtend in Fcp menu |  |  | Ron
8.15 | Production Work-flow | Validate Verify that admin can setup destinations with custom metadata requirements. | Verify that admin can setup destinations with custom metadata requirements. |  |  | Ron
8.16 | Production Work-flow | Validate Verify that transfers of FCP media after render is faster than real-time | Verify that after render the file transfers faster than real-time |  |  | Ron
8.17 | Production Work-flow | Validate Verify that FCP editor can see live feed, season, edit, graphics volumes. | Verify that FCP editor can see live feed, season, edit, graphics volumes. |  |  | Ron
8.18 | Production Work-flow | Validate Render and transfer must be faster than XDCAM50 media. | Render and transfer must be faster than XDCAM50 media. |  |  | Ron
8.19 | Production Work-flow | Validate 18 FCP stations publish simultaneously without issues | 18 FCP stations publish simultaneously without issues |  |  | Ron
8.2 | Production Work-flow | Validate 18 FCP stations edit individual games at the same time | 18 FCP stations edit individual games at the same time |  |  | Ron
8.21 | Production Work-flow | Validate 18 FCP stations edit same game at the same time | 18 FCP stations edit same game at the same time |  |  | Ron
8.22 | Production Work-flow | Validate 22 loggers logging different games at the same time | 22 loggers logging different games at the same time |  |  | Ron
8.23 | Production Work-flow | Validate All EVS XT channels play-out different feeds at same time | All EVS XT channels play-out different feeds at same time |  |  | Ron
8.24 | Production Work-flow | Validate All EVS XT channels play-out same feeds at same time | All EVS XT channels play-out same feeds at same time |  |  | Ron
8.25 | Production Work-flow | Validate 48 Dalet web clients searching and playing different clips at the same time | 48 Dalet web clients searching and playing different clips at the same time |  |  | Ron
8.26 | Production Work-flow | Validate 48 Dalet web clients searching and playing same clip at the same time | 48 Dalet web clients searching and playing same clip at the same time |  |  | Ron
8.27 | Production Work-flow | Validate 18 FCP Xtend clients searching and playing different clips at the same time | 18 FCP Xtend clients searching and playing different clips at the same time |  |  | Ron
8.28 | Production Work-flow | Validate 18 FCP Xtend clients searching and playing same clips at the same time | 18 FCP Xtend clients searching and playing same clips at the same time |  |  | Ron
8.29 | Production Work-flow | Validate Test FCP render and publish with Slo-mo outro in time line | Test FCP render and publish with Slo-mo outro in time line |  |  | Ron
8.3 | Production Work-flow | Validate Verify that in-record feed that is stopped early, does not blow away renders or disrupt playback in FCP or EVS. | Verify that in-record feed that is stopped early, does not blow away renders or disrupt playback in FCP or EVS. |  |  | Ron
8.31 | Production Work-flow | Validate 22 logging stations scrubbing/skipping different feeds at the same time. | 22 logging stations scrubbing/skipping different feeds at the same time. |  |  | Ron
8.32 | Production Work-flow | Validate 18 FCP stations scrubbing/skipping different feeds at the same time. | 18 FCP stations scrubbing/skipping different feeds at the same time. |  |  | Ron
8.33 | Production Work-flow | Validate 18 FCP stations scrubbing/skipping same feed at the same time. | 18 FCP stations scrubbing/skipping same feed at the same time. |  |  | Ron
8.34 | Production Work-flow | Validate 18 FCP stations test with dissolves, spot shadows, keys | 18 FCP stations test with dissolves, spot shadows, keys |  |  | Ron
8.35 | Production Work-flow | Validate User can create New Clip Dalet MediaLogger after search or browse in Dalet WebSpace | User can create New Clip Dalet MediaLogger after search or browse in Dalet WebSpace |  |  | Ron
8.36 | Production Work-flow | Validate Using MediaLogger the user is able to make shot selection (Mark-In & Mark-Out) and send the shots directly to Storyboarder Time line when editing is needed | Using MediaLogger the user is able to make shot selection (Mark-In & Mark-Out) and send the shots directly to Storyboarder Time line when editing is needed |  |  | Ron
8.37 | Production Work-flow | Validate Using MediaLogger the user is able to make shot selection (Mark-In & Mark-Out) and send the shots to Storyboarder Clip Bin to be trimmed | Using MediaLogger the user is able to make shot selection (Mark-In & Mark-Out) and send the shots to Storyboarder Clip Bin to be trimmed |  |  | Ron
8.38 | Production Work-flow | Validate Entire Titles (no Mark-In or Mark_Out) can also be moved to the Storyboarder time line | Entire Titles (no Mark-In or Mark_Out) can also be moved to the Storyboarder time line |  |  | Ron
8.39 | Production Work-flow | Validate Once the Storyboard is created the user is able preview the Storyboard, or selected segments in the Storyboard preview | Once the Storyboard is created the user is able preview the Storyboard, or selected segments in the Storyboard preview |  |  | Ron
8.4 | Production Work-flow | Validate The user is able to add segments to the Storyboard | The user is able to add segments to the Storyboard |  |  | Ron
8.41 | Production Work-flow | Validate Create EDL containing all media in Storyboard time line | Create EDL containing all media in Storyboard time line |  |  | Ron
8.42 | Production Work-flow | Validate Dalet automatically creates a high resolution of the corresponding media between Mark-in and Mark-Out | Dalet automatically creates a high resolution of the corresponding media between Mark-in and Mark-Out |  |  | Ron
8.43 | Production Work-flow | Validate After rendering a 'long Term' proxy for DaletPlus Windows clients and Dalet WebSpace web clients will be created by Rhozet and deposited in the proxy NAS | After rendering a 'long Term' proxy for DaletPlus Windows clients and Dalet WebSpace web clients will be created by Rhozet and deposited in the proxy NAS |  |  | Ron
8.44 | Production Work-flow | Validate Dalet Application Server will automatically discover the proxies, references them in it's DB and change the Status | Dalet Application Server will automatically discover the proxies, references them in it's DB and change the Status |  |  | Ron
8.45 | Production Work-flow | Validate Authorized user will have the ability to edit video material using the built-in Dalet MediaCutter video editing tool to finish a HD Clip | Authorized user will have the ability to edit video material using the built-in Dalet MediaCutter video editing tool to finish a HD Clip |  |  | Ron
8.46 | Production Work-flow | Validate The Dalet MediaCutter Time line enables the user to add voice-overs, do cut-to-cut editing manage audio levels and perform server-side conforming | The Dalet MediaCutter Time line enables the user to add voice-overs, do cut-to-cut editing manage audio levels and perform server-side conforming |  |  | Ron
8.47 | Production Work-flow | Validate When conforming an edit Time line done in MediaCutter, the Dalet Enterprise Edition application keeps track of the shot used in the editing of a finish piece | When conforming an edit Time line done in MediaCutter, the Dalet Enterprise Edition application keeps track of the shot used in the editing of a finish piece |  |  | Ron
8.48 | Production Work-flow | Validate DaletPlus workstations are used to purge media from the system | DaletPlus workstations are used to purge media from the system |  |  | Ron
8.49 | Production Work-flow | Validate Purge rules are Dalet user access controlled | Purge rules are Dalet user access controlled |  |  | Ron
8.5 | Production Work-flow | Validate Dalet can only purge media in Dalet aware storage and corresponding Watch Folders | Dalet can only purge media in Dalet aware storage and corresponding Watch Folders |  |  | Ron
9.01 | Worflow Sync | Validate that work-flows can be synchronized | Work-flows are synchronized |  |  | Mai
9.02 | Worflow Sync | Validate that media retention occurs | Media Retention occurs |  |  | Mai
9.03 | Worflow Sync | Validate that EVS rules are purged | EVS rules are purged |  |  | Mai
9.04 | Worflow Sync | Validate that MAM rules are purged | MAM rules are purged |  |  | Mai
9.05 | Worflow Sync | Validate that Archive rules are purged | Archive rules are purged |  |  | Mai
9.06 | Worflow Sync | Validate that MAM rules are migrated | MAM rules are migrated |  |  | Mai
9.07 | Worflow Sync | Validate that Archive rules are migrated | Archive rules are migrated |  |  | Mai
9.08 | Worflow Sync | Validate that Media Consolidation and storage (games, melts, pressers, tops and tails cut-downs) | Media Consolidation and storage (games, melts, pressers, tops and tails cut-downs) |  |  | Mai