## Worksheet
Administrative Support - Business Plan Tracking View
Item ID | Task Description | Responsible Person | Start Date | Due Date | Status | % Complete
A001 | Initial Business Concept Development | John Smith | 2023-10-01 | 2023-10-15 | Completed | 100%
A002 | Market Research & Analysis | Sarah Johnson | 2023-10-16 | 2023-11-30 | In Progress | 65%
A003 | Financial Projections Draft | Lisa Wong | 2023-11-01 | 2023-11-25 | In Progress | 45%
A004 | SWOT Analysis Report | Michael Brown | 2023-11-15 | 2023-12-05 | In Progress | 70%
A005 | Executive Summary Preparation | Emily Davis | 2023-12-01 | 2023-12-15 | Pending | 0%
A006 | Review & Finalize Plan Document | Robert Taylor | 2023-12-16 | 2023-12-31 | Pending | 0%
Total Tasks:6 ¦Completed:1 ¦In Progress:3 ¦Pending:2