## Worksheet
Task ID | Task Name | Start Date | End Date | Duration (Days) | Status | Progress (%)
TASK-001 | Plan Administrative Workflow | 2024-03-25 | 2024-04-15 | 21 | Pending
Hire Support Staff | Recruitment & Onboarding | 2024-03-30 | 2024-05-10 | 41 | Pending
Develop Document Templates | Create Standardized Forms | 2024-04-01 | 2024-05-15 | 45 | In Progress
Implement Digital Filing System | Deploy Cloud Storage Solution | 2024-05-15 | 2024-06-30 | 46 | In Progress
Train Staff on New Tools | Conduct Training Sessions | 2024-06-15 | 2024-07-31 | 46 | Pending
Audit Administrative Processes | Review & Optimize Workflows | 2024-07-15 | 2024-08-31 | 47 | Pending
Launch New Support System | Final Deployment & Monitoring | 2024-08-15 | 2024-10-31 | 77 | Pending
Total Duration: | [5 empty] | 276 Days