## Worksheet
Administrative Support - Gantt Chart (Analysis View)
Task ID | Task Name | Start Date | End Date | Status | Progress (%)
A001 | Project Kickoff Meeting | 2024-01-15 | 2024-01-15 | In Progress | 95%
A002 | Resource Allocation Planning | 2024-01-16 | 2024-01-31 | Completed | 100%
A003 | Document Preparation & Review | 2024-02-01 | 2024-02-15 | Completed | 100%
A004 | Meeting Scheduling & Coordination | 2024-02-16 | 2024-03-15 | In Progress | 75%
A005 | Travel & Logistics Arrangements | 2024-03-16 | 2024-04-15 | Not Started | 0%
M001 | Project Milestone - Phase 1 Complete | 2024-03-15 | 2024-03-15 | Milestone Reached | 100%
A006 | Monthly Reporting & Analytics | 2024-04-16 | 2024-12-31 | Not Started | 0%