## Worksheet
Administrative Support - Gantt Chart (Client View)
Task / Activity | Start Date | End Date | Progress & Timeline | Status
Project Overview: Administrative Support for Q3 2024
Document Preparation & Review | 2024-07-01 | 2024-07-15 |  | In Progress
Meeting Scheduling & Coordination | 2024-07-10 | 2024-08-15 |  | On Hold
Expense Report Processing | 2024-07-15 | 2024-08-31 |  | In Progress
Client Onboarding Support | 2024-08-01 | 2024-09-30 |  | Delayed
Monthly Reporting & Analytics | 2024-08-15 | 2024-09-15 |  | Not Started
Project Summary
Total Tasks |  |  | 5
Completed |  |  | 1 (20%)
In Progress |  |  | 2 (40%)
Delayed / On Hold |  |  | 2 (40%)
Notes & Updates
Client feedback requested for document finalization by July 12. Onboarding tasks delayed due to client availability.