## Worksheet
Administrative Support - Gantt Chart (Data Version)
Task ID | Task Name | Start Date | End Date | Status | % Complete
001 | Document Preparation | 2024-04-01 | 2024-04-15 | In Progress | 75%
002 | Email Correspondence Setup | 2024-04-03 | 2024-04-18 | In Progress | 65%
003 | Schedule Meetings | 2024-04-05 | 2024-04-17 | Not Started | 15%
004 | Data Entry & Validation | 2024-04-10 | 2024-05-15 | In Progress | 85%
005 | Monthly Report Compilation | 2024-04-12 | 2024-04-30 | In Progress | 95%
006 | Filing & Archiving System Update | 2024-04-15 | 2024-05-15 | Not Started | 10%
007 | Cross-departmental Coordination | 2024-04-20 | 2024-05-18 | In Progress | 55%
008 | Training Session Scheduling | 2024-04-25 | 2024-05-11 | In Progress | 70%
009 | Budget Tracking Update | 2024-05-01 | 2024-05-31 | Not Started | 5%
010 | Final Review & Submission | 2024-05-25 | 2024-06-15 | Not Started | 3%
Template Version: Data Version ¦ Created for Administrative Support Use ¦ April 2024