## Worksheet
Administrative Support - Detailed Gantt Chart
Task ID | Task Description | Start Date | End Date | Status | Progress (%) | % of Effort (Est.)
T01 | Project Planning & Initiation | 2023-10-02 | 2023-10-15 | Pending |  | 10%
T01.01 | Define Project Scope & Objectives | 2023-10-02 | 2023-10-05 | In Progress |  | 3%
T01.02 | Develop Project Charter | 2023-10-06 | 2023-10-15 | Pending |  | 7%
T02 | Resource Coordination & Scheduling | 2023-10-16 | 2023-11-15 | Pending |  | 25%
T02.01 | Identify & Assign Project Team | 2023-10-16 | 2023-10-25 | Pending |  | 8%
T02.02 | Set Up Communication Protocols | 2023-10-17 | 2023-11-5 | Pending |  | 6%
T03 | Documentation & Reporting | 2023-11-01 | 2024-01-31 | Pending |  | 40%
T03.01 | Prepare Monthly Progress Reports | 2023-11-15 | 2024-01-31 | Pending |  | 25%
T03.02 | Update Project Dashboard | 2023-11-18 | 2024-01-31 | Pending |  | 15%
M01 | Project Kickoff Meeting | 2023-10-06 | 2023-10-06 | Completed |  | 5%
M02 | Phase 1 Sign-Off | 2023-11-30 | 2023-11-30 | Pending |  | 5%
Total Project Effort: |  |  |  | 75% |  | 100%
Legend:Progress = Filled bar (color indicates completion level), Status reflects current stage, % Effort shows estimated allocation.