## Worksheet
Administrative Support - Extended Gantt Chart
Task / Activity | Start Date | End Date | Duration (Days) | Progress
Project Planning & Initiation
Define project scope and objectives | 2024-04-01 | 2024-04-05 | 5
Assemble project team and assign roles | 2024-04-02 | 2024-04-06 | 5
Document Management
Create centralized document repository | 2024-04-08 | 2024-04-15 | 8
Develop document classification system | 2024-04-10 | 2024-04-18 | 9
Meeting Coordination
Schedule weekly team meetings | 2024-04-01 | 2024-06-30 | 91
Prepare and distribute meeting agendas | 2024-04-01 | 2024-06-30 | 91
Reporting & Analytics
Generate weekly progress reports | 2024-04-08 | 2024-06-30 | 85
Compile monthly performance analytics | 2024-05-01 | 2024-07-31 | 93
Resource & Vendor Management
Onboard administrative vendors | 2024-04-15 | 2024-04-30 | 16
Monitor vendor performance and service levels | 2024-05-01 | 2024-12-31 | 365
Last updated on April 5, 2024 ¦ Gantt Chart Template - Administrative Support (Extended Style)