## Worksheet
Administrative Support - Gantt Chart Template
Template Type: Gantt Chart ¦ Style/Version: Home Use
Task ID | Task Description | Start Date | End Date | Status | Progress (%)
T001 | Document Organization & Filing System Setup | 2024-05-01 | 2024-05-15 | Completed | 100%
T002 | Daily Calendar Management & Scheduling | 2024-05-16 | 2024-06-30 | In Progress | 75%
T003 | Email & Communication Management | 2024-05-16 | 2024-06-30 | In Progress | 80%
T004 | Meeting Preparation & Minutes Documentation | 2024-05-16 | 2024-12-31 | In Progress | 60%
T005 | Travel Arrangements & Expense Reporting | 2024-06-15 | 2024-12-31 | Future Task | 0%
T006 | Inventory & Supply Management | 2024-07-01 | 2025-12-31 | Future Task | 0%
T007 | Monthly Reporting & Data Compilation | 2024-08-01 | 2025-12-31 | Future Task | 0%
T008 | Special Project Coordination (Q3) | 2024-10-15 | 2024-11-30 | Future Task | 0%
T009 | Annual Review Preparation & Documentation | 2025-11-15 | 2025-12-31 | Future Task | 0%
T010 | System Updates & Process Improvement Reviews | 2025-03-15 | 2025-06-30 | Future Task | 0%