## Worksheet
Administrative Support - Gantt Chart (Page 1)
Task | Start Date | End Date | Duration (Days) | Progress | Responsible
Project Initiation | 2024-01-05 | 2024-01-15 | 11 |  | Admin Team Lead
Document Preparation | 2024-01-16 | 2024-01-31 | 16 |  | Jane Doe, Admin Assistant
Vendor Onboarding | 2024-01-20 | 2024-02-15 | 37 |  | Mike Chen, Admin Coordinator
Milestone: Project Kickoff Meeting | 2024-01-15 | 2024-01-15 | 1 |  | Project Manager
Daily Operations Support | 2024-01-05 | 2024-12-31 | 365 |  | All Admin Staff
Administrative Support - Gantt Chart (Page 2)
Task | Start Date | End Date | Duration (Days) | Progress | Responsible
Meeting Scheduling & Coordination | 2024-01-05 | 2024-12-31 | 365 |  | Sarah Lee, Office Manager
Travel Arrangements | 2024-01-10 | 2024-12-31 | 365 |  | David Brown, Admin Assistant
Milestone: Q1 Review Meeting | 2024-04-15 | 2024-04-15 | 1 |  | All Stakeholders
Report Compilation & Distribution | 2024-03-25 | 2024-04-15 | 19 |  | Jane Doe, Admin Assistant
Internal Training Sessions | 2024-05-10 | 2024-06-15 | 37 |  | Training Coordinator
Administrative Support - Gantt Chart (Page 3)
Task | Start Date | End Date | Duration (Days) | Progress | Responsible
Annual Audit Preparation | 2024-08-01 | 2024-11-30 | 99 |  | Jane Doe, Admin Assistant
Equipment & Inventory Audit | 2024-09-15 | 2024-10-31 | 46 |  | Mike Chen, Admin Coordinator
Milestone: Year-End Closeout | 2024-12-31 | 2024-12-31 | 1 |  | All Departments
Performance Review Coordination | 2024-10-01 | 2024-11-30 | 60 |  | Sarah Lee, Office Manager
Policy Updates & Documentation | 2024-11-01 | 2024-12-31 | 90 |  | Admin Team Lead