## Worksheet
Administrative Support - Gantt Chart (Planning View)
Task ID | Task Name | Start Date | End Date | Duration (Days) | Status | Progress
TSK-001 | Project Kick-off Meeting | 2024-04-05 | 2024-04-05 | 1 | Completed
TSK-002 | Create Administrative Plan | 2024-04-06 | 2024-04-15 | 10 | In Progress
TSK-003 | Resource Allocation & Scheduling | 2024-04-16 | 2024-04-25 | Not Started
TSK-004 | Document Preparation & Review | 2024-04-26 | 2024-05-10 | Not Started
TSK-005 | Training Sessions (Team) | 2024-05-11 | 2024-05-17 | Not Started
TSK-006 | Final Review & Approval | 2024-05-18 | 2024-05-21
TSK-007 | Project Closure & Handover | 2024-05-22 | 2024-05-31