## Worksheet
Task | Start Date | End Date | Progress | Notes
Project Initiation | 2024-01-01 | 2024-01-05 | 100% | Kick-off meeting, team allocation
Document Preparation | 2024-01-06 | 2024-01-15 | 85% | Drafting standard operating procedures
Stakeholder Review | 2024-01-16 | 2024-01-20 | 55% | Feedback collection from department heads
Finalization & Approval | 2024-01-21 | 2024-01-25 | 30% | Final edits, sign-off by management
Implementation Phase | 2024-01-26 | 2024-01-31 | 5% | Rollout of new procedures across teams
Overall Progress |  |  | 75% | On track for completion