## Worksheet
Administrative Support Planner - Manager View
Task ID | Task Description | Assigned To | Schedule & Status |  |  | Priority Level | Deadline
|  |  | Start Date | End Date | Status
#AS-001 | Monthly Budget Review Preparation | Jane Smith | 2024-03-01 | 2024-03-15 | In Progress | High | 2024-03-15
#AS-002 | Team Meeting Scheduling & Agenda Distribution | Mike Johnson | 2024-03-10 | 2024-03-18 | Pending Approval | Medium | 2024-03-18
#AS-003 | Office Supplies Replenishment Order | Sarah Williams | 2024-03-12 | 2024-03-16 | Completed | Low | 2024-03-16
#AS-004 | Annual Employee Performance Review Documentation | David Brown | 2024-03-15 | 2024-03-31 | To Do | High | 2024-03-31
#AS-005 | Client Onboarding Package Preparation | Lisa Garcia | 2024-03-18 | 2024-03-25 | In Progress | High | 2024-03-25
#AS-006 | IT Support Ticket Resolution Follow-Up | Chris Lee | 2024-03-14 | 2024-03-19 | Closed (Pending Feedback) | Medium | 2024-03-19
#AS-007 | Quarterly Report Compilation & Review | Elena Martinez | 2024-03-16 | 2024-03-31 | In Progress | High | 2024-03-31
#AS-008 | Travel Arrangements for Executive Team | Amy Clark | 2024-03-17 | 2024-03-29 | To Do | High | 2024-03-29
#AS-009 | Document Archiving & Indexing Update | Raj Patel | 2024-03-13 | 2024-03-17 | Completed | Low | 2024-03-17
#AS-010 | Maintenance Request Coordination for Office Spaces | Tina Wong | 2024-03-20 | 2024-03-31 | In Progress | Medium | 2024-03-31
Total Tasks: |  |  |  |  | 10 | High Priority: |  | 5