## Worksheet
Project Plan - Administrative Support
Task ID | Task Description | Owner | Start Date | End Date | Status | Budget (USD)(Planned)
ADP-001 | Initial Project Setup & Planning | Jane Doe | 2024-04-01 | 2024-04-15 | In Progress | $3,500.00(Est.)
ADP-002 | Resource Allocation & Team Briefing | John Smith | 2024-04-16 | 2024-04-30 | Completed | $5,750.00(Est.)
ADP-003 | Document Management System Implementation | Sarah Lee | 2024-05-01 | 2024-05-15 | In Progress | $8,900.00(Est.)
ADP-004 | Vendor Onboarding & Contract Negotiation | Michael Brown | 2024-05-16 | 2024-06-15 | Delayed (Pending Approval) | $7,300.00(Est.)
ADP-005 | Monthly Reporting & Dashboard Integration | Lisa Wong | 2024-06-16 | 2024-07-15 | In Progress | $4,850.00(Est.)
ADP-006 | Project Review & Final Documentation | Jane Doe | 2024-07-16 | 2024-08-31 | In Progress | $6,150.00(Est.)
Total Project Budget: | [5 empty] | $46,450.00(Est.)