## Project Plan - Analysis View
Project Plan - Analysis View
Task ID | Task Description | Assigned To | Start Date | End Date | Status | % Complete
T001 | Project Initiation & Kickoff Meeting | Admin Team Lead | 2023-10-01 | 2023-10-05 | In Progress | 75%
T002 | Resource Allocation Planning | HR Coordinator | 2023-10-06 | 2023-10-15 | To Do | 0%
T003 | Departmental Requirement Gathering | Project Manager | 2023-10-16 | 2023-10-25 | In Progress | 45%
T004 | Data Collection & Validation Process Setup | Data Analysts | 2023-10-26 | 2023-11-10 | To Do | 0%
T005 | Documentation & Reporting Framework Development | Admin Support Staff | 2023-11-11 | 2023-11-25 | To Do | 0%
Total Progress: | [5 empty] | 38%
This Project Plan - Analysis View is for Administrative Support. Last Updated: October 26, 2023.