## Project Plan - Client View
Project Plan - Client View
Purpose: Administrative Support
Task ID | Task Name | Description | Start Date | End Date | Status | Assigned To(Role)
TASK001 | Project Kickoff Meeting | Initial planning and alignment meeting with stakeholders. | 2023-10-02 | 2023-10-03 | In Progress | Jane Smith (Project Manager)
TASK002 | Resource Allocation Plan | Define team roles and resource requirements. | 2023-10-04 | 2023-10-15 | Pending | Mike Johnson (Admin Lead)
TASK003 | Document Repository Setup | Establish secure folder structure and access controls. | Note: Requires IT coordination.2023-10-16 | 2023-10-25 | Not Started | Lisa Tran (Admin Coordinator)
TASK004 | Status Reporting Template Creation | Design and finalize weekly reporting format.(Includes KPIs, risks, and updates) | 2023-10-18 | 2023-10-30 | In Progress | Raj Patel (Reporting Officer)
TASK005 | Budget Review and Approval | Finalize and submit budget proposal for client approval.(Includes contingency planning) | 2023-11-01 | 2023-11-15 | Not Started | Susan Lee (Finance Admin)
TASK006 | Client Feedback Session 1 | Present project progress and gather feedback.(Scheduled for bi-weekly review) | 2023-11-05 | 2023-11-06 | Not Started | Alex Turner (Client Relations)
Note:This template is designed for client viewing. All dates and status updates are subject to change based on project progression and stakeholder feedback.