## Worksheet
Task | Start Date | End Date | Responsible | Status
Project Initiation | 2023-10-01 | 2023-10-05 | Admin Team Lead | Completed
Resource Allocation | 2023-10-06 | 2023-10-10 | HR Coordinator | In Progress
Budget Approval | 2023-10-11 | 2023-10-15 | Finance Manager | Pending
Work Plan Development | 2023-10-16 | 2023-10-25 | Project Coordinator | Not Started
Stakeholder Communication | 2023-10-18 | 2023-10-30 | Admin Assistant | Not Started
Monthly Review Meeting | 2023-11-05 | 2023-11-05 | Project Manager | Not Started