## Worksheet
Task ID | Task Name | Assigned To | Start Date | End Date | Status | Priority
P001 | Project Initiation Meeting | Jane Doe | 2023-10-01 | 2023-10-05 | Completed | High
P002 | Define Project Scope | John Smith | 2023-10-06 | 2023-10-15 | In Progress | High
P003 | Develop Work Breakdown Structure (WBS) | Alice Johnson | 2023-10-16 | 2023-10-25 | Not Started | Medium
P004 | Create Project Schedule (Gantt Chart) | Mike Brown | 2023-10-26 | 2023-11-05 | Not Started | Medium
P005 | Resource Allocation Plan | Susan Lee | 2023-11-06 | 2023-11-15 | Not Started | Low
P006 | Risk Assessment & Mitigation Planning | David Wilson | 2023-11-16 | 2023-11-25 | Not Started | High
P007 | Finalize Project Plan Document | Jane Doe | 2023-11-26 | 2023-12-05 | Not Started | Medium