## Worksheet
Task ID | Task Name | Start Date | End Date | Duration (days) | Resource Assigned | Status(Not Started/In Progress/Completed) | Dependencies(Task IDs)
1 | Project Initiation & Planning | 2024-04-01 | 2024-04-15 | 15 | Project Manager, Admin Assistant | Not Started | -
2 | Create Project Scope Document | 2024-04-16 | 2024-04-18 | 3 | Project Manager, Admin Assistant | In Progress | 1
3 | Develop Work Breakdown Structure (WBS) | 2024-04-19 | 2024-04-25 | 7 | Project Manager, Team Leads | In Progress | 1
4 | Prepare Budget Proposal & Approvals | 2024-04-26 | 2024-05-10 | 15 | Finance Officer, Admin Assistant | In Progress | 3
5 | Hire & Onboard Project Team Members | 2024-05-11 | 2024-05-31 | 21 | HR Coordinator, Admin Assistant | In Progress | 3.0, 4.0
6 | Design Project Timeline & Milestones | 2024-06-01 | 2024-06-15 | 15 | Project Manager, Admin Assistant | In Progress | 5.0, 4.0 (partial)
7 | Conduct Kickoff Meeting | 2024-06-16 | 2024-06-16 | 1 | All Project Team, Admin Assistant | In Progress | 6.0 (completed)
8 | Execute Phase 1: Requirements Gathering & Analysis | 2024-06-17 | 2024-07-15 | 30 | Business Analysts, IT Team, Admin Assistant | In Progress | 7.0 (completed)
9 | Develop Detailed Project Schedule & Gantt Chart | 2024-07-16 | 2024-07-31 | 16 | Project Manager, Admin Assistant | In Progress | 8.0 (completed)
10 | Solicit & Evaluate Vendor Proposals (if applicable) | 2024-08-01 | 2024-08-15 | 15 | Purchasing Team, Admin Assistant | In Progress | 6.0 (completed), 9.0 (partial)
11 | Finalize Project Plan & Obtain Approvals | 2024-08-16 | 2024-08-31 | 16 | Project Manager, Steering Committee, Admin Assistant | In Progress | 9.0 (completed), 10.0 (partial)
12 | Begin Phase 2: System Design & Prototyping | 2024-09-01 | 2024-10-31 | 61 | IT Team, Designers, Admin Assistant | In Progress | 7.0 (completed), 11.0 (partial)
13 | Milestone Review: Phase 2 Completion | 2024-11-01 | 2024-11-05 | 5 | Project Manager, Team Leads, Admin Assistant | In Progress | 12.0 (partial)
14 | Begin Phase 3: Development & Testing | 2024-11-06 | 2025-01-31 | 87 | IT Team, QA Testers, Admin Assistant | In Progress | 13.0 (completed)
15 | Milestone Review: Phase 3 Completion | 2025-02-01 | 2025-02-15 | 15 | Project Manager, QA Lead, Admin Assistant | In Progress | 14.0 (completed)
16 | Prepare Training Materials & Documentation | 2025-02-16 | 2025-03-15 | 30 | Training Specialist, Admin Assistant | In Progress | 14.0 (completed)
17 | Conduct User Training Sessions | 2025-03-16 | 2025-04-15 | 31 | Training Team, Admin Assistant | In Progress | 16.0 (completed)
18 | Begin Phase 4: Deployment & Go-Live Support | 2025-04-16 | 2025-05-31 | 46 | IT Team, Admin Assistant, Support Staff | In Progress | 17.0 (completed)
19 | Milestone Review: Go-Live Success & System Stability | 2025-06-01 | 2025-06-15 | 15 | Project Manager, IT Lead, Admin Assistant | In Progress | 18.0 (completed)
20 | Closure Activities: Final Reports & Lessons Learned | 2025-06-16 | 2025-07-31 | 46 | Project Manager, Admin Assistant, Team Leads | In Progress | 19.0 (completed)
Project Summary
Total Duration (Planned) |  |  | 14 months (2024-04-01 to 2025-07-31)
Total Tasks |  |  | 20
Current Status (Overall) |  |  | In Progress