## Worksheet
Task ID | Task Description | Assigned To | Start Date | End Date | Status | % Complete
A-001 | Project Initiation & Planning | John Doe | 2023-10-02 | 2023-10-15 | In Progress
A-002 | Resource Allocation Review | Jane Smith | 2023-10-16 | 2023-10-25 | Not Started
A-003 | Department Coordination Meeting | Mike Brown | 2023-10-26 | 2023-11-05 | Not Started
A-004 | Document Template Development | Sarah Wilson | 2023-11-06 | 2023-11-15 | Not Started
A-005 | Approval Process Setup | David Lee | 2023-11-16 | 2023-11-30 | Not Started
A-006 | Training Session Preparation | Linda Garcia | 2023-12-01 | 2023-12-10 | Not Started
A-007 | Final Review & Sign-Off | John Doe | 2023-12-11 | 2023-12-15 | Not Started
Project Overall Status