## Project Plan - Employee View
Project Plan - Employee ViewPurpose: Administrative Support
Task | Start Date | End Date | Status | Assigned To | Priority
Project Kickoff Meeting | 2024-01-15 | 2024-01-15 | Completed | Jane Smith | Highest
Define Project Scope | 2024-01-16 | 2024-01-25 | In Progress | John Doe | High
Create Work Breakdown Structure (WBS) | 2024-01-26 | 2024-01-31 | Not Started | Alice Brown | Medium
Resource Allocation & Assignment | 2024-02-01 | 2024-02-05 | Not Started | Robert Green | High
Status Reporting Setup | 2024-02-06 | 2024-02-15 | Not Started | Jane Smith | Medium
Milestone Review Meeting #1 | 2024-02-16 | 2024-02-16 | Pending | All Team Members | Low
Total Tasks: |  |  |  |  | 6