## Worksheet
Project Plan - Administrative SupportExtended Version ¦ Prepared for Administrative Operations
PROJECT OVERVIEW
Project Name | Administrative Support Initiative 2024 |  |  | Owner | Office of Administration, Jane Doe (Director)
Start Date | 2024-01-15 | End Date | 2024-12-31 | Status | Planning Phase (Scheduled)
Objective | Enhance internal administrative efficiency through standardized processes, digital transformation of records, and team training to support organizational growth.
KEY MILESTONES
Milestone | Target Date | Owner | Status | Description | Deliverable | Notes / Dependencies
Preliminary Process Audit | 2024-02-15 | Admin Audit Team | In Progress | Review all current administrative workflows and document inefficiencies. | Audit Report v1.0 | Requires access to departmental systems and staff interviews.
Process Optimization Plan Finalized | 2024-03-31 | Jane Doe, Director | Pending | Develop and approve revised administrative procedures. | Optimization Blueprint v2.0 | Pending approval from Executive Committee.
Digital Document Management System (DMS) Implementation | 2024-06-30 | IT & Admin Teams | Pending | Deploy DMS platform across departments. | DMS Go-Live Report | Integration with existing HR and finance systems required.
Staff Training Program Completion | 2024-09-15 | Training Coordinator, Mark Lee | Pending | Certify all administrative staff on new tools and processes. | Training Completion Certificates | All staff must complete training by deadline.
RESOURCE ALLOCATION
Role/Position | Team Member | Hours/Week (Est.) | Status | Notes / Responsibilities
Project Manager (Admin) | Jane Doe | 20 | Active | Overall oversight, decision-making, reporting to executive team.
Process Analyst | Sarah Kim | 15 | Active | Conduct audits, data analysis, workflow redesign.
IT Systems Coordinator | Robert Chen | 18 | Inactive (Pending) | Systems integration and DMS setup; currently onboarding.
Budget Summary (Total: $120,000) |  |  |  |  | Allocated | Remaining
Software & Tools (DMS, Training Platforms) |  |  |  |  | $48,000 | $12,500
Staff Training & Development |  |  |  |  | $22,000 | $19,758
Consulting & Process Review Services |  |  |  |  | $30,000 | $7,321
RISK MANAGEMENT
Risk Factor | Probability (1-5) | Impact (1-5) | Risk Score | Mitigation Strategy & Owner
Low staff engagement in training | 3 | 4 | 12 | Incentivize participation with recognition program; led by Training Coordinator.
IT integration delays | 4 | 5 | 20 | Schedule bi-weekly syncs with IT team; buffer time built into schedule.
NOTES & COMMENTS
This document is a living template. All sections subject to review and update monthly by the Project Steering Committee. Last Updated: 2024-01-10 ¦ Version: 1.5 (Extended)