## Project Plan - Financial View
PROJECT PLAN - FINANCIAL VIEW
Phase / Task | Start Date | End Date | Budget (USD) | Actual Spend (USD) | % of Budget Used | Status | Owner | Milestone Progress (%)
Phase 1: Project Planning & Initiation
Requirements Gathering | 2024-01-05 | 2024-01-19 | $15,000.00 | $13,567.89 | 90.45% | In Progress | Jane Smith | 88%
Phase 2: Design & Development Setup
System Architecture Design | 2024-01-15 | 2024-01-31 | $8,500.00 | $7,934.25 | 93.34% | In Progress | Juan Perez | 92%
Phase 3: System Development & Testing
Frontend Development | 2024-01-25 | 2024-03-15 | $65,000.00 | $48,793.67 | 75.07% | In Progress | Sarah Williams | 68%
Phase 4: Deployment & Training
System Rollout & Integration | 2024-03-18 | 2024-03-31 | $45,000.00 | $19,867.56 | 44.15% | In Progress | Mark Johnson | 32%
Phase 5: Project Closure & Evaluation
Final Review & Documentation | 2024-04-01 | 2024-04-15 | $7,500.00 | $3,987.36 | 53.16% | Not Started | Linda Brown | 15%
Total Project Budget & Actual Spend |  |  | $141,000.00 | $94,150.73 | 66.77% |  |  | 52%
Notes: This financial view tracks project budget allocation, actual expenditures, and performance metrics. Status updates are reviewed weekly.