## Project Plan - Freelancer Style
Task | Start Date | Due Date | Status | Assigned To | Budget (USD)
Project Kickoff & Planning | 2023-10-05 | 2023-10-15 | In Progress | Jane Doe (Freelancer) | $450.00
Client Onboarding Documentation | 2023-10-16 | 2023-10-25 | Pending | John Smith (Freelancer) | $350.00
Weekly Status Reports & Meetings | 2023-10-16 | 2024-12-31 | In Progress | Jane Doe (Freelancer) | $5,800.00
Database & File Organization System Setup | 2023-11-01 | 2023-11-15 | Pending | John Smith (Freelancer) | $850.00
Client Communication & Email Management | 2023-11-16 | 2024-12-31 | In Progress | Jane Doe (Freelancer) | $7,500.00
Monthly Performance Review & Reporting | 2023-11-30 | 2024-11-30 | Pending | John Smith (Freelancer) | $2,500.00
Project Closure & Final Documentation | 2024-11-30 | 2024-12-31 | Pending | Jane Doe (Freelancer) | $650.00
Total Estimated Cost: |  |  |  |  | $18,100.00