## Worksheet
Project Plan - Administrative Support
Task ID | Task Description | Responsible Party | Start Date | End Date | Status | % Complete
P001 | Define project scope and objectives | Project Manager | 2024-04-01 | 2024-04-15 | Complete | 100%
P002 | Assign team members and roles | HR & Admin Lead | 2024-04-16 | 2024-04-30 | Complete | 100%
P003 | Develop budget and cost projections | Finance Coordinator | 2024-05-01 | 2024-05-15 | Complete | 100%
P004 | Create administrative workflows and documentation | Process Analyst | 2024-05-16 | 2024-06-15 | Ongoing | 75%
P005 | Conduct staff training sessions | Training Coordinator | 2024-06-16 | 2024-07-31 | Ongoing | 55%
P006 | Deploy new administrative systems and tools | IT Support & Admin Lead | 2024-08-01 | 2024-09-30 | Delayed (Pending Approval) | 35%
M101 | Final Project Review and Handover | Project Manager | 2024-10-01 | 2024-10-31 | Planned | 0%
P007 | Collect feedback and performance metrics | Admin Analyst | 2024-11-01 | 2024-11-30 | Not Started | 0%
Project Duration:April 1, 2024 – November 30, 2024
Status as of:April 5, 2024 ¦ Total Tasks: 7 ¦ On Track: 3 ¦ Delayed: 1