## Worksheet
Project Plan - Administrative Support
Template Type: Project Plan ¦ Style/Version: Multi Page
Project Summary
Project Name: | Administrative Support Enhancement Initiative
Project Manager: | Jane Doe
Start Date: | 2024-01-15
End Date: | 2024-06-30
Status: | In Progress
Budget: | $85,000.00
Key Milestones
Milestone | Due Date | Status | Description
Project Kickoff Meeting | 2024-01-20 | Completed | Initial planning session with stakeholders.
Resource Allocation Finalized | 2024-01-31 | In Progress | Assignment of team members and tools finalized.
Process Documentation Complete | 2024-03-15 | Not Started | All administrative workflows documented.
Pilot Phase Implementation | 2024-04-10 | Not Started | Limited deployment to two departments.
Full Rollout Completion | 2024-06-15 | Not Started | All departments fully transitioned.
Final Review & Sign-off | 2024-06-30 | Not Started | Closing review and project approval.
Task Schedule (Page 2)
Task ID | Task Description | Assigned To | Start Date | End Date
T001 | Categorize Administrative Functions | Jane Doe (PM) | 2024-01-15 | 2024-01-25
T002 | Identify Pain Points in Current Workflow | Mark Johnson (Analyst) | 2024-01-18 | 2024-01-31
T003 | Develop New Standard Operating Procedures (SOPs) | Sarah Lee (SOP Lead) | 2024-02-01 | 2024-03-15
T004 | Design Digital Workflows and Templates | Alex Kim (IT) | 2024-03-16 | 2024-04-15
T005 | Conduct Training Sessions (Pilot) | Lisa Brown (HR Trainer) | 2024-04-16 | 2024-05-15
T006 | Deploy to All Departments | Marcus Taylor (IT Lead) | 2024-05-16 | 2024-06-15
T007 | Capture Feedback & Adjust Processes | Jane Doe (PM) | 2024-06-16 | 2024-06-25
T008 | Final Project Report & Presentation | Jane Doe (PM) | 2024-06-26 | 2024-06-30
Resource Allocation (Page 3)
Role | Name | Department | Time Commitment (%) | Total Hours (Est.)
Project Manager | Jane Doe | Admin Office | 50%
Business Analyst | Mark Johnson | Data Processing Unit
SOP Development Lead | Sarah Lee | Operations Division | 40%
IT Developer/Workflow Designer | Alex Kim
HR Training Specialist
IT Deployment Lead | Marcus Taylor | Tech Support Team
Quality Assurance Reviewer
Risk Register (Page 4)
Risk ID | Description | Impact Level | Mitigation Plan
R001
R002 | IT system compatibility issues with legacy tools. | Moderate (3/5) | Conduct integration testing early; involve IT in planning.
R003
R004 | Training sessions not attended by key staff. | Moderate (3/5) | Schedule training during non-peak hours; send reminders.
R005
Budget Breakdown (Page 5)
Category | Planned Budget | Actual Spend | Balanced Status
External Consultants (SOP, QA) | $15,000.00 | $8,523.67 | Under Budget (-$6,476.33)
Training Materials & Delivery | $6,500.00 | $4,321.75 | Under Budget (-$2,178.25)
Remaining Balance | $16,654.58