## Worksheet
Project Plan - Administrative Support
Task ID | Task Description | Responsible Person | Start Date | End Date | Status
P001 | Project Initiation and Planning | Project Manager | 2023-10-01 | 2023-10-15 | In Progress
P002 | Resource Allocation & Scheduling | Admin Coordinator | 2023-10-16 | 2023-10-25 | Not Started
P003 | Document Preparation and Review | Office Administrator | 2023-10-26 | 2023-11-05 | Not Started
P004 | Stakeholder Communication Plan | Communication Specialist | 2023-11-06 | 2023-11-15 | Not Started
P005 | Milestone Review Meeting Preparation | Project Manager | 2023-11-16 | 2023-11-20 | Not Started
P006 | Final Documentation & Approval Process | Office Administrator | 2023-11-21 | 2023-11-30 | Not Started
Total Duration: |  |  |  |  | 60 days
Note:This template is designed for office use and administrative support project planning. Adjust dates and responsibilities as needed.