## Worksheet
Task ID | Task Description | Responsible Person | Start Date | End Date | Status
P001 | Initial Project Setup and Planning Session | Jane Doe | 2024-04-01 | 2024-04-03 | In Progress
P002 | Resource Allocation and Team Assignment | John Smith | 2024-04-04 | 2024-04-05 | Not Started
P003 | Develop Administrative Workflow Documentation | Sarah Lee | 2024-04-06 | 2024-04-15 | Not Started
P004 | Procurement of Office Supplies and Equipment | Michael Brown | 2024-04-16 | 2024-04-18 | Not Started
P005 | Training Session for Administrative Team | Jane Doe | 2024-04-19 | 2024-04-21 | Not Started
P006 | Project Review and Status Reporting (Week 1) | John Smith | 2024-04-22 | 2024-04-23 | Not Started
P007 | Implementation of New Scheduling System | Sarah Lee | 2024-04-24 | 2024-05-15 | Not Started
P008 | Final Review and Documentation Handover | Michael Brown | 2024-05-16 | 2024-05-17 | Not Started
P009 | Project Closure and Feedback Collection | Jane Doe | 2024-05-18 | 2024-05-19 | Not Started
Total Duration: |  |  |  |  | 49 days