## Project Plan - Planning View
Task ID | Task Name | Start Date | End Date | Duration (Days) | Responsible Person | Status | % Complete
T001 | Project Initiation & Planning | 2024-04-01 | 2024-04-15 | 15 | Jane Smith | In Progress | 75%
T002 | Resource Allocation & Scheduling | 2024-04-16 | 2024-04-30 | 15 | John Doe | In Progress | 60%
T003 | Administrative Infrastructure Setup | 2024-05-01 | 2024-05-15 | 15 | Sarah Johnson | Not Started | 0%
T004 | Documentation & Reporting Framework Development | 2024-05-16 | 2024-06-15 | 31 | Marcus Lee | Not Started | 0%
T005 | Training & Onboarding Session Preparation | 2024-06-16 | 2024-07-15 | 31 | Lisa Brown | Not Started | 0%
Total Duration: | [6 empty] | 107 days
Note:This project plan is a planning view template for administrative support activities. Update task statuses and progress regularly to maintain accuracy.