## Worksheet
Project Plan - Quarterly Administrative Support
Task ID | Task Description | Responsible Person | Start Date | End Date | Status | Priority | Notes
TP-001 | Project Kickoff Meeting | Jane Smith | 2024-01-05 | 2024-01-15 | In Progress | High | Initial planning and team alignment.
TP-002 | Develop Administrative Workflow Documentation | Mike Johnson | 2024-01-16 | 2024-01-31 | To Do | Medium | Include templates and approval processes.
TP-003 | Coordinate Vendor Onboarding Process | Sarah Lee | 2024-01-20 | 2024-02-15 | In Progress | High | Finalize contracts and access permissions.
TP-004 | Monthly Team Performance Review Setup | David Brown | 2024-01-25 | 2024-03-31 | To Do | Medium | Scheduled for the 1st of each month.
TP-005 | Quarterly Budget Review and Reporting | Lisa Wong | 2024-02-15 | 2024-03-15 | To Do | High | Submit to Finance by March 18.
TP-006 | Implement Digital Document Management System | Tom Reed | 2024-03-15 | 2024-03-31 | To Do | High | Limited resources; requires IT collaboration.
Total Tasks: | [6 empty] | 6