## Project Plan - Small Business
Task ID | Task Name | Start Date | End Date | Assignee | Status | % Complete
T001 | Project Kickoff Meeting | 2023-10-05 | 2023-10-05 | Jane Doe | Completed | 100%
T002 | Create Project Charter | 2023-10-06 | 2023-10-12 | John Smith | In Progress | 75%
T003 | Develop Work Breakdown Structure (WBS) | 2023-10-13 | 2023-10-19 | Jane Doe | In Progress | 50%
T004 | Identify Resources and Assignments | 2023-10-20 | 2023-10-26 | John Smith | Not Started | 0%
T005 | Risk Assessment and Mitigation Planning | 2023-10-27 | 2023-11-02 | Jane Doe | Not Started | 0%
T006 | Finalize Project Plan and Approval | 2023-11-03 | 2023-11-09 | John Smith | Not Started | 0%
Note:This project plan is designed for small business administrative support. Adjust dates and tasks as needed based on actual project requirements.