## Worksheet
Project Plan - Administrative Support
Startup Style ¦ Purpose: Administrative Support
Phase | Task Name | Description | Responsible Person | Start Date | End Date | Status
Initiation | Define Project Scope | Establish objectives, deliverables, and key stakeholders. | Jane Doe | 2024-04-01 | 2024-04-05 | In Progress
Planning | Create Administrative Workflow | Design documentation, approval processes, and digital filing systems. | John Smith | 2024-04-06 | 2024-04-15 | To Do
Execution | Deploy Support Tools | Implement calendar management, email templates, and meeting scheduling. | Alice Johnson | 2024-04-16 | 2024-04-30 | To Do
Execution | Staff Training Session | Conduct training on new administrative procedures and tools. | Bob Wilson | 2024-05-01 | 2024-05-05 | To Do
Closing | Review & Finalize Documentation | Compile all project materials and hand over to team lead. | Jane Doe | 2024-05-06 | 2024-05-10 | To Do
Closing | Project Handover & Feedback Session | Present results and collect feedback from stakeholders. | John Smith | 2024-05-11 | 2024-05-15 | To Do
Total Duration: | [5 empty] | 2024-04-01 to 2024-05-15