## Project Plan - Summary View
Project Plan - Summary View
Purpose: Administrative Support ¦ Template Type: Project Plan ¦ Style/Version: Summary View
Phase | Task Description | Start Date | End Date | Status | Responsible Team/Person
Initiation | Define project scope and objectives | 2024-01-05 | 2024-01-15 | In Progress | Jane Doe - Project Manager
Planning | Develop detailed work breakdown structure (WBS) | 2024-01-16 | 2024-01-31 | Pending | John Smith - Lead Analyst
Execution | Resource allocation and task assignment | 2024-02-01 | 2024-03-15 | Not Started | Lisa Chen - Admin Coordinator
Execution | Campaign coordination and documentation | 2024-03-16 | 2024-05-31 | Not Started | Lisa Chen - Admin Coordinator
Monitoring & Control | Weekly progress tracking and reporting | 2024-02-01 | 2024-05-31 | Not Started | Jane Doe - Project Manager
Closing | Final review and project documentation handover | 2024-06-01 | 2024-06-15 | Not Started | Jane Doe - Project Manager / Lisa Chen - Admin Coordinator