## Worksheet
Task ID | Task Description | Responsible Team Member(s) | Start Date | End Date | Status | Notes/Comments
TASK001 | Project Kickoff Meeting | Team Lead, Admin Coordinator | 2024-04-01 | 2024-04-01 | In Progress | Agenda prepared and circulated.
TASK002 | Develop Project Timeline | Project Manager, Admin Assistant | 2024-04-02 | 2024-04-15 | Pending | Requires input from all team leads.
TASK003 | Allocate Resources & Budget Approval | Finance Team, Admin Manager | 2024-04-16 | 2024-04-25 | To Do | Submit budget request by 04/18.
TASK004 | Set Up Shared Drive & Document Templates | IT Support, Admin Coordinator | 2024-04-18 | 2024-04-25 | In Progress | Drive structure finalized.
TASK005 | Weekly Status Meeting (Scheduled) | All Team Members | 2024-04-19 | Ongoing | Completed | Meeting held every Friday at 10:00 AM.
TASK006 | Review and Finalize Project Plan | Project Manager, Admin Lead | 2024-04-26 | 2024-05-15 | Pending | Final sign-off required.
TASK007 | Launch Project & Begin Execution Phase | All Teams | 2024-05-16 | 2024-11-30 | To Do | Project officially begins.
Project Milestones
Milestone 1:Project Approval Signed - April 25, 2024 Milestone 2:First Deliverable Submitted - June 30, 2024 Milestone 3:Mid-Project Review Meeting - September 15, 2024 Milestone 4:Final Project Delivery & Sign-Off - November 30, 2024