## Project Plan - Tracking View
Task ID | Task Description | Assigned To | Start Date | Due Date | Status | % Complete
Administrative Support - Project Plan (Tracking View)
TSK-001 | Project Kickoff Meeting | Jane Smith | 2024-04-15 | 2024-04-15 | In Progress | 85%
TSK-002 | Develop Project Schedule | David Lee | 2024-04-16 | 2024-04-18 | In Progress | 65%
TSK-003 | Resource Allocation Planning | Sarah Johnson | 2024-04-17 | 2024-04-19 | Not Started | 0%
MSK-01 | Milestone: Project Plan Approved | Project Manager | 2024-04-19 | 2024-04-19 | Not Started | 0%
TSK-004 | Distribute Project Documentation | Jane Smith | 2024-04-20 | 2024-04-21 | Not Started | 0%
TSK-005 | Daily Status Reporting Setup | David Lee | 2024-04-16 | 2024-04-30 | In Progress | 75%
TSK-006 | Weekly Review Meeting Coordination | Sarah Johnson | 2024-04-18 | 2024-11-30 | In Progress | 55%
MSK-02 | Milestone: First Monthly Review Complete | Project Manager | 2024-05-15 | 2024-05-15 | Not Started | 0%
Total Tasks: | [5 empty] | 8