## Project Template - Client View
Task ID | Task Description | Assigned To | Status | Start Date | End Date | Budget (USD)
TASK001 | Initial Project Kickoff Meeting | Jane Smith | Completed | 2023-10-01 | 2023-10-05 | $5,000.00
TASK002 | Requirements Gathering Workshop | John Doe | In Progress | 2023-10-15 | 2023-10-31 | $8,500.00
TASK003 | Design Phase Review | Alice Johnson | Not Started | 2023-11-15 | 2023-12-05 | $6,750.00
TASK004 | Development Phase Implementation | Robert Brown | Not Started | 2023-12-15 | 2024-01-31 | $45,000.00
TASK005 | User Acceptance Testing (UAT) | Sarah Wilson | Not Started | 2024-02-15 | 2024-03-15 | $15,000.00
Total Project Budget: | [5 empty] | $80,250.00