## Worksheet
Administrative Support Project Template
Task ID | Task Description | Assigned To | Start Date | End Date | Status
T001 | Define project scope and objectives | Project Manager | 2024-03-01 | 2024-03-05 | In Progress
T002 | Develop administrative workflow documentation | Administrative Lead | 2024-03-06 | 2024-03-12 | In Progress
T003 | Coordinate with department heads for input | Coordinator | 2024-03-13 | 2024-03-19 | In Progress
T004 | Implement standardized filing and record-keeping system | Records Manager | 2024-03-20 | 2024-03-31 | In Progress
T005 | Conduct team training on new procedures | Training Specialist | 2024-04-01 | 2024-04-05 | In Progress
T006 | Review and finalize project documentation | Project Manager | 2024-04-06 | 2024-04-10 | In Progress
T007 | Submit final project report to stakeholders | Project Manager | 2024-04-11 | 2024-04-15 | In Progress