## Worksheet
Project Timeline - Analysis View
Task ID | Task Description | Assigned To | Start Date | End Date | Status | % Complete
PT001 | Project Initiation & Planning | John Smith | 2023-10-05 | 2023-10-15 | Completed | 100%
PT002 | Requirements Gathering | Jane Doe | 2023-10-16 | 2023-10-31 | Completed | 100%
PT003 | Design Phase (UI/UX) | Alex Johnson | 2023-11-01 | 2023-11-15 | Active | 75%
PT004 | Development Sprint 1 | Maria Garcia | 2023-11-16 | 2023-12-05 | Active | 45%
PT005 | Data Integration Setup | Robert Brown | 2023-12-06 | 2023-12-15 | Delayed | 30%
PT006 | User Acceptance Testing (UAT) | Sarah Wilson | 2023-12-18 | 2024-01-15 | Active | 35%
PT007 | Final Deployment & Go-Live | James Taylor | 2024-01-16 | 2024-01-31 | Active | 5%
Project Summary
Total Tasks:7
Completed:2 (28.6%)
In Progress:4 (57.1%)
Delayed:1 (14.3%)
Total Duration:90 days (From Oct 5, 2023 - Jan 31, 2024)
Legend
Completed- Task finished successfully
Active- Ongoing task with progress
Delayed- Task behind schedule or impacted by delays