## Worksheet
Task | Start Date | End Date | Status | Assigned To
Project Initiation | 2023-10-01 | 2023-10-05 | In Progress | Jane Smith
Requirements Gathering | 2023-10-06 | 2023-10-15 | Not Started | John Doe
Design Phase | 2023-10-16 | 2023-10-30 | Not Started | Sarah Johnson
Development | 2023-10-31 | 2023-12-15 | Not Started | Mike Brown
Testing & QA | 2023-12-16 | 2024-01-05 | Not Started | Lisa White
Deployment | 2024-01-06 | 2024-01-15 | Not Started | Daniel Lee
Closure & Review | 2024-01-16 | 2024-01-20 | Not Started | Jane Smith