## Worksheet
Task | Start Date | End Date | Status | Responsible Party
Project Kickoff Meeting | 2023-10-01 | 2023-10-03 | In Progress | Admin Team
Requirement Gathering | 2023-10-04 | 2023-10-15 | Not Started | Client Liaison
Design Phase Approval | 2023-10-16 | 2023-10-25 | Not Started | Design Team
Development Phase 1 | 2023-10-26 | 2023-11-15 | Not Started | Development Team
Testing & QA | 2023-11-16 | 2023-12-05 | Not Started | QA Team
User Acceptance Testing (UAT) | 2023-12-06 | 2023-12-15 | Not Started | Client Representative
Deployment & Go-Live | 2023-12-16 | 2023-12-18 | Not Started | IT Operations
Post-Launch Review | 2023-12-19 | 2023-12-25 | Not Started | Admin Team