## Worksheet
Project | Phase | Start Date | End Date | Status | Responsible Person
Administrative Support Initiative | Planning & Setup | 2023-10-01 | 2023-10-15 | In Progress | Jane Smith
Administrative Support Initiative | Data Collection | 2023-10-16 | 2023-10-31 | Not Started | Mike Johnson
Administrative Support Initiative | Data Processing | 2023-11-01 | 2023-11-15 | Not Started | Sarah Lee
Administrative Support Initiative | Review & Validation | 2023-11-16 | 2023-11-30 | Not Started | Daniel Brown
Administrative Support Initiative | Closure & Reporting | 2023-12-01 | 2023-12-15 | Not Started | Jane Smith