## Worksheet
Project Timeline - Administrative Support
Detailed Schedule for Administrative Operations and Support Activities
Phase | Task Description | Start Date | End Date | Duration (Days) | Status | Responsible Team/Personnel
Initiation | Project Kickoff Meeting & Scope Definition | 2023-10-01 | 2023-10-05 | 5 | In Progress | Jane Smith, Admin Lead
Planning | Resource Allocation & Workload Assessment | 2023-10-06 | 2023-10-15 | 10 | Pending Review | Derek Lee, Operations Manager
Execution | Document Management System Setup & Training | 2023-10-16 | 2023-10-31 | 16 | In Progress | Sarah Kim, IT Support & Training Lead
Execution | Office Supply Procurement & Inventory Audit | 2023-10-18 | 2023-11-05 | 18 | Pending Review | Ricardo Mendez, Procurement Specialist
Execution | Daily Administrative Coordination & Scheduling | 2023-10-16 | 2023-11-30 | 45 | In Progress | All Admin Staff (Rotational)
Maintenance | Monthly Report Generation & Compliance Checks | 2023-11-01 | 2023-11-30 | 30 | Pending Review | Lisa Wang, Finance & Admin Analyst
Closure | Final Documentation Submission & Project Review Meeting | 2023-12-01 | 2023-12-05 | 5 | Pending Start | Jane Smith, Admin Lead & Team
Note:This timeline is subject to adjustment based on team availability and project scope changes. All dates are estimated.