## Worksheet
Employee View - Project Timeline
Task ID | Task Description | Assigned To | Start Date | End Date | Status
T101 | Project Kickoff Meeting | Jane Doe | 2023-10-05 | 2023-10-05 | Completed
T102 | Requirement Gathering | John Smith | 2023-10-06 | 2023-10-15 | In Progress
T103 | Design Phase - Wireframes | Alice Johnson | 2023-10-16 | 2023-10-25 | Not Started
T104 | Development - Frontend | Robert Brown | 2023-10-26 | 2023-11-15 | Not Started
T105 | Development - Backend | Lisa Wong | 2023-10-26 | 2023-11-30 | Not Started
T106 | Testing & QA | Michael Lee | 2023-12-01 | 2023-12-15 | Not Started
T107 | User Training Session | Jane Doe | 2023-12-18 | 2023-12-20 | Not Started
T108 | Project Closure & Review | John Smith | 2023-12-21 | 2023-12-25 | Not Started
Last updated: October 5, 2023 ¦ Project Manager: Sarah Thompson