## Worksheet
Project Timeline - Administrative Support
Task ID | Task Description | Start Date | End Date | Status | Responsible Person
A001 | Project Kickoff Meeting | 2023-10-05 | 2023-10-05 | Completed | Jane Smith
A002 | Resource Allocation Planning | 2023-10-06 | 2023-10-12 | In Progress | John Doe
A003 | Documentation Setup & Review | 2023-10-13 | 2023-10-19 | Not Started | Sarah Johnson
A004 | Weekly Status Meetings (Bi-weekly) | 2023-10-16 | 2024-12-31 | In Progress | Jane Smith
A005 | Vendor Contract Finalization | 2023-10-20 | 2023-11-10 | Not Started | Mike Brown
A006 | Training Session Preparation | 2023-11-13 | 2023-11-24 | Not Started | Sarah Johnson
A007 | Final Reporting & Submission | 2023-11-25 | 2023-11-30 | Not Started | Jane Smith
Total Tasks: |  |  |  | 7
Completed: |  |  |  | 1
In Progress: |  |  |  | 2
Not Started: |  |  |  | 4