## Worksheet
Freelancer Project Timeline - Administrative Support
Template Type: Project Timeline ¦ Purpose: Administrative Support
Task ID | Task Description | Start Date | End Date | Status | Assigned To
TASK-001 | Initial Project Kickoff Meeting | 2024-01-15 | 2024-01-15 | Completed | Jane Smith
TASK-002 | Document Collection & Organization | 2024-01-16 | 2024-01-25 | In Progress | Mike Johnson
TASK-003 | Draft Project Schedule & Timeline | 2024-01-26 | 2024-01-31 | Pending | Sarah Lee
TASK-004 | Client Communication & Updates | 2024-02-01 | 2024-12-31 | Pending | Jane Smith
TASK-005 | Monthly Reporting Preparation | 2024-02-15 | 2024-12-31 | Pending | Mike Johnson
TASK-006 | Final Project Review & Documentation Closure | 2024-12-15 | 2024-12-31 | Pending | Sarah Lee