## Worksheet
Project Timeline - Administrative Support
Phase / Task | Start Date | End Date | Status | Owner | Budget Allocated (USD)
Project Initiation | 2024-01-05 | 2024-01-15 | Completed | Jane Doe | $3,500
Resource Planning & Allocation | 2024-01-16 | 2024-01-31 | In Progress | Mike Chen | $5,800
Administrative Infrastructure Setup | 2024-02-01 | 2024-02-15 | Completed | Sarah Williams | $8,300
Document Management System Implementation | 2024-02-16 | 2024-03-15 | In Progress | Daniel Kim | $15,600
Team Training & Onboarding | 2024-03-16 | 2024-03-31 | Completed | Laura Evans | $6,750
Phase Review & Evaluation | 2024-04-01 | 2024-04-15 | Pending | Jane Doe | $3,950
Final Reporting & Documentation | 2024-04-16 | 2024-05-15 | Pending | Sarah Williams | $7,200
Total Project Cost: | $51,100 |  |  |  | $51,100
Generated on¦ Project ID: PS-2024-ADM-001