## Project Timeline - Manager View
Project Timeline - Manager View
Task ID | Task Name | Owner | Start Date | End Date | Status | Budget (USD)
T001 | Project Kickoff Meeting | John Doe | 2025-04-01 | 2025-04-03 | In Progress | $1,500
T002 | Requirement Gathering Phase | Jane Smith | 2025-04-04 | 2025-04-15 | In Progress | $3,800
T003 | Design Phase Approval | Mike Johnson | 2025-04-16 | 2025-04-30 | Pending | $5,200
T004 | Development Sprint 1 | Sarah Williams | 2025-05-01 | 2025-05-14 | Pending | $8,900
T005 | Testing & QA Cycle | David Brown | 2025-05-15 | 2025-06-14 | Pending | $7,300
T006 | User Training & Documentation | Lisa Taylor | 2025-06-15 | 2025-07-14 | Pending | $4,600
T007 | Final Project Review & Handover | James Clark | 2025-07-15 | 2025-07-31 | Pending | $3,100
Total Project Budget:$44,400