## Project Timeline - Monthly
Project Timeline - Monthly ¦ Purpose: Administrative Support
Month | Task/Activity | Responsible Party | Status | Start Date | End Date
January 2024 | Project Initiation & Planning | Admin Team Lead | In Progress | 01/05/2024 | 01/15/2024
January 2024 | Budget Approval Submission | Finance Coordinator | Not Started | 01/10/2024 | 01/31/2024
February 2024 | Resource Allocation & Scheduling | Project Manager | In Progress | 02/01/2024 | 02/15/2024
February 2024 | Team Onboarding Sessions | HR Administrator | Not Started | 02/05/2024 | 02/18/2024
March 2024 | Phase One Implementation | Operations Team | In Progress | 03/01/2024 | 03/31/2024
March 2024 | Mid-Project Review Meeting | Project Manager & Admin Lead | Not Started | 03/15/2024 | 03/17/2024
April 2024 | Performance Monitoring & Adjustments | Data Analyst & Admin Team | Not Started | 04/01/2024 | 04/15/2024
May 2024 | Final Deliverables Preparation | All Team Members | Not Started | 05/01/2024 | 05/31/2024
Project Summary: Administrative Support ¦ Expected Completion: May 31, 2024