## Worksheet
Project Timeline - Administrative Support
Phase | Task Description | Start Date | End Date | Status | Responsible Party
Initiation | Project Kickoff Meeting | 2024-01-15 | 2024-01-15 | In Progress | Jane Smith - Project Manager
Planning | Develop Detailed Work Plan | 2024-01-16 | 2024-01-25 | To Do | Mike Johnson - Admin Lead
Planning | Resource Allocation and Scheduling | 2024-01-26 | 2024-01-31 | To Do | Lisa Chen - HR Coordinator
Execution | Procurement of Supplies and Equipment | 2024-02-01 | 2024-02-15 | To Do | Daniel Rodriguez - Procurement Officer
Execution | Staff Training and Onboarding | 2024-02-16 | 2024-03-15 | To Do | Sarah Williams - Training Coordinator
Monitoring & Control | Weekly Progress Reviews | 2024-02-16 | 2024-03-15 | To Do | All Team Members
Closing | Final Documentation and Reporting | 2024-03-16 | 2024-03-31 | To Do | Jane Smith - Project Manager
Closing | Project Evaluation and Feedback Session | 2024-04-01 | 2024-04-15 | To Do | All Stakeholders
© 2024 Office Use Template - Administrative Support ¦ Project Timeline
This document is intended for internal use and may be modified as needed.