## Worksheet
Task ID | Task Name | Start Date | End Date | Duration (days) | Resource Assigned | Status
T001 | Project Initiation | 2023-10-01 | 2023-10-05 | 5 | Jane Smith | In Progress
T002 | Requirement Gathering | 2023-10-06 | 2023-10-15 | 10 | John Doe, Lisa Brown | To Do
T003 | Design Phase | 2023-10-16 | 2023-10-31 | 16 | Alex Johnson, Sarah Lee | To Do
T004 | Development Phase | 2023-11-01 | 2023-11-30 | 30 | Michael Taylor, Emma White | To Do
T005 | Testing & QA | 2023-12-01 | 2023-12-15 | 15 | Rachel Green, David Kim | To Do
T006 | Deployment & Training | 2023-12-16 | 2024-01-15 | 31 | Jane Smith, John Doe | To Do
T007 | Project Closure & Review | 2024-01-16 | 2024-01-31 | 16 | Lisa Brown, Sarah Lee | To Do